ÉÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍ»
                      º E A S Y  P R O J E C T  (tm) º
                      º                              º
                      º         USER GUIDE           º
                      º         Version 2.5          º
                      ÈÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍÍ¼

                 A Project Management and Tracking System
              for the I.B.M. Personal Computer and Compatibles



                  (c) Copyright 1987, 1988 Parcell Software
                            All Rights Reserved



















                              Parcell Software
                            948 Manchester Course
                              Geneva, Il  60134
                               (312) 232-6328

                           CompuServe ID:  72250,1356






                                              ÚÄÄÄÄÄÄÄÄÄ¿
                                        ÚÄÄÄÄÄÁÄÄÄ¿     ³              (tm)
                                      ÄÄ³         ³o    ³ÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄ
                                        ³   ÚÄÄÄÄÄÁÐÄÄ¿ ³  Association of
                                        ³   ³         ³ÄÙ  Shareware
                                        ÀÄÄÄ³    o    ³    Professionals
                                      ÄÄÄÄÄÄ³    º    ³ÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄÄ
                                            ÀÄÄÄÄÐÄÄÄÄÙ    MEMBER





                          E A S Y  P R O J E C T  (tm)


                               Registration


    Easy Project is a Shareware program.

    You are encouraged to copy and share this program with other users. 
    No fee can be charged for such copying and distribution except for
    a nominal charge to defray expenses.

    If you find this program useful, we trust you to send a $39.00
    payment. Registration covers a single PC only.  Site licenses
    available upon request.

    Shareware constitutes a viable, low cost alternative to many
    commercially available products.  Shareware distribution gives users
    an opportunity to try software before buying it.  If you try a
    Shareware program and continue to use it, you are expected to
    register.  Your support is important and greatly appreciated.

    All registered users will receive:
                - Latest version of Easy Project with Shareware screen
                  disabled
                - Printed User Guide
                - Notification of updates
                - Free technical support

    Please use the form below when registering your copy.

   -----------------------------------------------------------------------

                          E A S Y  P R O J E C T
                                   2.5
                             Registration Form


    Name:                                              Date:          

    Address:                                     

                                                

                                                    
    Where did you hear about Easy Project:


    Registration is $39.00 and covers a single PC only.
    Please send a check or money order to :

                             Parcell Software
                           948 Manchester Course
                             Geneva, Il  60134






                       E A S Y  P R O J E C T  (tm)


                               Introduction


         Easy Project is a project management tool for the I.B.M. and
         compatible personal computers.  Easy Project is designed to be an
         easy to learn, practical, and efficient method for planning,
         tracking, and controlling all types of projects.

         Easy Project features:

             1.  User defined project phases (20 maximum)
             2.  Unlimited number of resources per project
             3.  User defined tasks (1000 per project)
             4.  User defined subordinate tasks or items (100 per task)
             5.  Fast data entry with multiple resource assignments
                 per task
             6.  Automatic scheduling and schedule maintenance
             7.  Gantt charts showing planned vs. actual dates
                 with variable scales
             8.  Extensive reporting including work plans, status reports,
                 and earned value accrual reporting
             9.  Online context sensitive help screens
            10.  dBASE III file compatibility

         Sample data is provided to assist in learning Easy Project.


         Disclaimer

             Parcell Software specifically disclaims any warranty, either
             expressed or implied, including but not limited to the
             implied warranties of merchantability and fitness for a
             particular use.

             In no event shall Parcell Software be liable for any special,
             consequential, or other damages, including loss of profit
             arising out of the us of this program.


         Trademarks

             Easy Project is a trademark of Parcell Software
             I.B.M. is a registered trademark of the I.B.M Corporation.
             dBASE III is a registered trademark of Ashton-Tate, Inc.





                       E A S Y  P R O J E C T  (tm)


                            System Requirements
                            

     Hardware
          I.B.M. PC/XT/AT/PS2 or 100% Compatible with at least 256K RAM

     Monitor
          Any

     Printer
          Over 40 different printers are supported.  To print Gantt
          charts using graphic characters, your printer must support
          the I.B.M. character set.

     Software
          DOS 2.x or 3.x
          CONFIG.SYS File
               A CONFIG.SYS file must be in the root directory of the
               boot disk.  This file should contain the following two
               records:
                    BUFFERS = 24
                    FILES = 24
               These values are minimum values.
               Re-boot DOS after making these changes.


                               Installation

     Hard Disk
          To install Easy Project on a hard disk system, place your copy
          of Easy Project in drive A and type:
                       INSTALLH

          This installation procedure will create a sub-directory on
          your hard disk of \EP and copy the necessary files.

     2 Floppy System

          1.  Make a backup of your Easy Project disk.
          2.  Using backup copy in drive A and blank formatted disk
              in drive B, type:  INSTALLF <enter>

              This process will copy all necessary data files to drive
              B and keep system files on drive A.  Label the disk in
              drive A "EP System" and the disk in drive B "EP Data".





                       E A S Y  P R O J E C T  (tm)


                           Starting Easy Project

     Hard Disk

          From the \EP directory, type:  EP <enter>

     2 Floppy System
 
         With the EP System disk in drive A and the EP Data disk
         in drive B, type :  EP <enter>




     NOTE:  The first time you execute Easy Project, choose the
            Utilities option from the Main Menu.  From this menu,
            configure both your monitor and your printer.  After
            making your monitor and printer choices, exit the system
            and re-enter to have the monitor configuration take effect.








                       E A S Y  P R O J E C T  (tm)



                             Data Entry Notes


       On all Easy Project screens and menus, the cursor can be controlled 
       in the following fashion:

    Key                         Result

<--|  (Enter)          Proceeds to the next field.  When
                       pressed while the cursor is in the
                       last field of a screen or menu, all
                       data will be saved.

PgDn                   Exits the screen saving all changes.

Esc                    Exits the screen without saving any
                       changes.

Up Arrow               Moves cursor to previous field.

Down Arrow             Moves cursor to next field.

<-                     Moves cursor backward one space.

 ->                    Moves cursor forward one space.

F5                     Deletes record while in Resource or
                                    Task update screens.

F1                     At any time while in Easy Project,
                                    help is available by pressing 'F1'.
                                    Easy Project will recognize what field
                                    or menu the request came from, and
                                    then display the appropriate text.

     Three heavily used fields will provide additional HELP when F1 is
     prossed:

          Project Number:  Will list all current projects on file.

          Task Number:     Will list all current tasks for a particular
                           project.

          Resource:        Will list all current resources for a
                           particular project.





                       E A S Y  P R O J E C T  (tm)


                                 Main Menu


     The Main Menu is the driver for Easy Project.  On this and all
     other menus, enter the number choice for the function you want.


     The components of the Main Menu are:

              Set Up Project Parameters
              Used to create project numbers, project descriptions,
              phase descriptions and set Gantt scales.

              Add/Change/Delete Resources
              Used for adding and maintaining resource data.

              Add/Change/Delete Tasks
              Used for adding and maintaining task detail data.

              Automatic Schedule Generation
              Schedule work plans automatically.

              Gantt Charts
              Produce Gantt charts for a project or phase showing
              original vs. current task dates.

              Reports
              Generate nine different reports including work plans,
              status reports and summary reports.  This function contains
              its own menu.

              Utilities
              Used to configure system and provide sundry utility
              file handling.  This function contains its own menu.

              Registration Information
              How to register Easy Project.

              Exit to DOS
              Return to operation system.







                       E A S Y  P R O J E C T  (tm)


                          Creating a New Project


       Easy Project is designed for quick project creation.  After
       spending a short time entering project data, Gantt charts and
       reports will become available.

       Follow this process when creating a new project:

           1.  Choose 'Set Up Project Parameters' from the Main Menu and
               enter project number, descriptions, phase descriptions and
               appropriate Gantt scale information.

           2.  Choose 'Add/Change/Delete Resources' from the Main Menu and
               add resource data for the project.  Resources will be
               identified by assigning them a unique user defined code.

           3.  Choose 'Add/Change/Delete Tasks' from the Main Menu to
               enter individual tasks to the project. (See Notes On
               Entering Tasks)

           4.  If you want Easy Project to calculate estimated schedule
               dates, choose 'Automatic Schedule Generation' from the Main
               Menu. (See Notes on Automatic Scheduling)

           5.  At this point, Gantt charts and/or reports may be produced.






                       E A S Y  P R O J E C T  (tm)


                         Set Up Project Parameters

       Easy Project has the ability to store data from several different
       projects at one time.  Each of those projects can have different base
       parameters.

       Before task or resource data can be entered for a particular
       project, certain parameters or criteria must be defined.

Project Number

             Every project must have its own unique project number.  This
             number is used to tell the system what project should be
             retrieved.  This number can be composed of any combinations of 
             characters or numbers (5 character maximum).

             NOTE:  Pressing 'F1' while on the project number field will 
             provide a list of all currently used numbers.

Project Name

             The Project Name is used to identify the project.  This 
             description will appear on all screens and reports.

Project Description

             To further define a project, use these fields.  The data 
             entered here will print on all reports.

Phase Descriptions

             For most projects, it is better to divide the project into
             smaller, more manageable phases.  Examples of phases could be:

                  1.  Lay foundation
                  2.  Framing
                  3.  Plumbing
                        OR
                  1.  Feasibility Study
                  2.  Design and Analysis
                  3.  Programming
                  4.  Acceptance

             Easy Project permits 20 different phases to be defined for one
             particular project.  The descriptions entered here will appear 
             on project summary reports.

Gantt Scale

             Flexible Gantt scales can be chosen to insure the most
             complete view of a project.  Each symbol on the chart can 
             represent from 1 to 6 days or weeks.  For projects of short 
             duration, a scale in days is probably more appropriate.




                       E A S Y  P R O J E C T  (tm)


                        Add/Change/Delete Resources



       Before task data can be entered, resource information must be 
       established.  Resources may consist of human type
       (employees, consultants, etc.) or fixed type (materials, capital
       expenses, etc.).


Field Descriptions

Identifier:  Each resource must be assigned a unique
             identifier.  This identifier could be a name,
             initials or an account code.  The identifier
             can be up to 6 characters and is alphanumeric.

             NOTE:  Pressing F1 while the cursor is in the
                    Identifier field will produce a list of
                    all resources already assigned to the project.

Name:        Enter the full name or description of the
             resource.

Rate:        The charge rate for the resource.

Type:        Choose either Hourly, Daily, or Fixed. If
             Fixed is chosen, this resource will not be
             automatically scheduled.

Dept:        Enter a department code for the resource.  This
             code may be up to 3 characters and is
             alphanumeric.
             NOTE:  This is an optional entry but is required
                    to produce departmentalized reports.

Useage:      Used to identify how many hours this resource
             works in one day.  (not needed for Fixed types)

Source:      An optional entry to further describe the
             resource.
                Example:  EMP = Employee
                          CON = Consultant

Note 1 &
Note 2:      An optional entry to use for any purpose.




                          E A S Y  P R O J E C T


                          Add/Change/Delete Tasks


       Task definition is the heart of project management.  Easy Project 
       permits for practical task creation and maintenance.  Before sitting 
       down and entering data, plan what logical order your tasks will
       follow and if possible, divide your project into phases.  Once your 
       data has been entered, refinement and maintenance is easy.

Field Definitions

Task:                  Enter the two digit phase number plus
                       three digit task number for this task.
                       Refer to 'Notes on Entering Tasks' for
                       choosing task numbers.

Item:                  Each task can consist of numerous
                       subordinate tasks or items.  Enter an
                       item number in this field. (optional)

Predecessor:           Use this field to tie tasks to a
                       proceeding or parent task.  Refer to
                       'Assigning Predecessors'.

Description:           Enter the description for this task.
                       This description will appear on all
                       reports and Gantt charts.

   Milestone:          If this task in considered a Milestone
                       in the project, enter 'Y'.

Resource:              Enter the resource identifier of the
                       resource assigned to this task.  A
                       maximum of four different resources
                       may be assigned to a particular task.

Est. Time:             Enter the amount of time (hours/days)
                       this task is expected to take to
                       complete this task.

Time To-Date:          Enter the amount of time this resource
                       has taken thus far for this task.

Original Start/Stop:   Enter the original or planned start
                       and stop date for this task.

Current Start/Stop:    Enter the current start and stop date
                       for this task.

Note 1 & Note 2:       To be used for any purpose.

Remaining:             Enter the time remaining for this
                       task.  The system will default to
                       the difference between estimated and
                       time to-date.





                       E A S Y  P R O J E C T  (tm)


Notes on Entering Tasks

Every task number consists of the following elements:
                Task Number  - 2 character phase number (01-20) plus
                               3 character task number (user defined)
                Item Number  - 2 characters, user defined (optional)
                Predecessor  - 7 characters, made up of (Phase + Task +
                               Item)

             Keep in mind that most reports are produced in task number 
             order. Using sequential task numbers of 001, 002, etc. within 
             each phase is recommended.

             Item number is meant as a subordinate task.  This is an
             optional entry but is useful in breaking down a large main 
             task.  Again, it's useful to use sequential item numbers 
             within each task number.

             Predecessor designates what task, if any, the current task is 
             dependent upon.  This field is also optional and will default 
             to its own task and item number.  If this is used, it should 
             consist of the phase, task and item number of the preceding 
             task.

Assigning Predecessors

             Predecessor numbers should be assigned using the parent or 
             host task number.  Several tasks can all contain the same
             predecessor number.  If no predecessor is assigned, the system 
             will default to the task number.

   Sample Task Numbers

          Task Field  =  01-002
          Item Field  =  03
          Predecessor =  01-002 03
          Definition:  This task belongs to phase 1, task equals 002 and
                       this is the third item for task 002.
                       This task is not dependent on any other task so the
                       predecessor field defaults to the phase, task and
                       item number.

          Task Field  = 01-003
          Item Field  = 01
          Predecessor = 01-002 03

          Definition:  This task belongs to phase 1, task equals 003 and
                       this is the first item for task 003.
                       This task is dependent on the task from the first
                       example (its parent task).




                          E A S Y  P R O J E C T


Automatic Schedule Maintenance

             If an original start or stop date is changed, for an existing 
             task, the automatic scheduler will be invoked adjusting both 
             original and current start/stop dates.  This adjustment will 
             occur only for tasks assigned the same predecessor.  You will 
             have the ability to override the proposed dates.

             Likewise, if a current start or stop date is changed, the 
             automatic scheduler will be invoked to adjust current dates 
             only.

Marking Tasks Complete

             For the purpose of the Project Status Report, Easy Project 
             considers a task complete when time remaining equals zero and 
             estimated or time to-date is greater than zero.




                       E A S Y  P R O J E C T  (tm)


                       Automatic Schedule Generation


       Easy Project will automatically calculate original start and stop
       dates based on the estimated time assigned to each task.

       To calculate dates, enter the project number followed by the base
       start date.  The base start date should be the date the project may
       begin.


     Schedule Screen Display

       As the schedule generates, each task and the newly calculated dates
       are displayed.  After the screen fills, you have the ability
       to change or override the calculated date.  Pressing <ESC> aborts
       the update process and the records will not be updated.

       Use the <ENTER> key to advance the cursor.  When the screen
       is completely updated, these dates will be used to update both the
       original and the current start and stop dates for the tasks.


      Notes on Dependencies

       For automatic scheduling and Gantt charts, dependencies should be
       created using the following example:

             In the case of tasks 001, 002, 003 and 004 being dependent
             upon the respective prior task (004 on 003, 003 on 002, etc.)
             assign tasks 002, 003, and 004 dependent to task 001.

             Think of task 001 as the parent task and then place the
             dependent tasks in task number order.

Notes on Scheduling

             1.  In the case of multiple resource tasks, the resource
                 taking the greatest amount of time will be used in
                 calculating the schedule. (the display reflects this)

             2.  Any task which has a fixed type resource will be ignored.

             3.  On the Resource update screen, the Useage field should
                 reflect the total number of hours the resource works
                 in one day. Use this for both hourly and daily type
                 resources.

             4.  Weekends will be taken into consideration when
                 calculating the schedule.





                        E A S Y  P R O J E C T  (tm)


                                Gantt Chart

       Easy Project's Gantt charts are designed to give a graphic display 
       of a projects planned vs. actual progress.

       Two different types of charts may be produced:

             1.  A chart displaying task for one particular phase in
                 task number order.

             2.  A chart displaying the entire project with tasks grouped
                 by dependencies.

       In order for a task to be displayed, it must have an Original Start
       Date.


    Scale Options

       Refer to Set Up Project Parameters on how to set the Gantt scale.  
       It may be changed at any time during the project.


Output Options

Easy Project offers three options for generating Gantt charts:

          1.  (D)isplay - The chart will be displayed on your monitor.
                          If the scale is set to 1 day, a view of
                          2 months will be displayed.

          2.  (P)rint - The chart will be printed in compressed format.
                        With a scale set to 1 day, a view of approximately
                        4 months will be printed.

          3.  (F)ile -  The chart will be written to a disk file named
                        GANTT.PRN.  This is an ASCII file that may be
                        printed through DOS or by using another print
                        utility program.  If the scale is set to 1 day,
                        a view of approximately 6 months will be printed.





                       E A S Y  P R O J E C T  (tm)


                                Report Menu


       Many helpful reports can be instantly generated either online or 
       sent to your printer.  Due to space limitations, some reports are 
       printed in compressed format - thus giving more detail than when 
       displayed online.

       Sample copies of all reports are contained at the end of this 
       manual.

              Work Plan By Task - Produces a detailed work plan for
              a particular phase in task number order.

              Work Plan By Resource - Produces a detailed work plan for
              the entire project in order of task original start date
              within resource.

              Work Plan Project Summary - Summarizes all phases of a
              project plan giving a concise report.

              Work Plan Resource Summary - Produces a departmentalized
              resource summary either for a particular phase or the entire
              project.

              Project Status Report (Plan vs. Actual) - A to-date status
              report for the entire project.

              Project Status Summary (Actual) - Summarizes all project
              phases showing actual costs and current dates.

              Project Resource Summary (Actual) - Shows departmental
              break down of actual costs by individual resource.

              Earned Value Report - A to-date report detailing cost
              accruals.

              Resource List - Gives a detailed list of all resources
              assigned to a particular project.

              Exit - Return to the Main Menu.






                           E A S Y  P R O J E C T  (tm)



                                Utility Menu


    The Utility Menu consists of various functions that may be used for
    file handling or system configuration.

    NOTE:  Be sure to backup all Easy Project files on a regular basis.  
           This will help in recovering from any potential disasters.


Reindex All Files

             Easy Project uses several index files which permits fast data
             retrieval.  These index files are not compatible with dBASE or
             any other known applications.  All files with the extension of
             .NTX should never be deleted.

             If the file integrity of your files is every in question,
             choose the reindex option.  File integrity may degrade due to
             abnormal termination of the system.

             It can never hurt the system to reindex files.


Delete (Pack) Marked Records

             When task or resource data is deleted using the 'F5' key, 
             they (records) are actually marked for deletion but physically 
             remain on file.  These records are unavailable for normal use.

             The delete option on this menu will physically delete all 
             marked records.  Once this option is exercised, the marked 
             records can no longer be used or recovered.


Undelete (Recall) Records

             This option will seek all records that have been marked for 
             deletion (and not packed), and recall or make them available 
             again for processing.

             NOTE:  This option will recall all records from all project 
             from all files regardless of project number.





                       E A S Y  P R O J E C T  (tm)


                         Utility Menu (continued)


Delete Project

             This function will delete all tasks, resources and related 
             records for a particular project.

             To use, first enter the project number to delete.  Next, you 
             will be prompted to verify that you really want to delete the 
             project.  Answering 'N' will bypass any deletions.  If 
             verified, records are marked for deletion.


Copy or Clone Project

             On occasion, you may want to create a project that has many 
             similar tasks as another project previously entered.  The copy
             option will take a current project and duplicate all tasks and 
             resources using a new project number.  The old project remains 
             intact with no changes.  


Rebuild Files from Importing

             Easy Project database files (.DBF) are dBASE III compatible 
             and can be exported directly into many other applications.  
             Exporting may provide useful for additional reporting or mass 
             updating.

             If files are exported and then imported into Easy Project, 
             they must be rebuilt.  This function will automatically 
             rebuild index files and all necessary relations.

             NOTE:  Exercise caution when updating Easy Project files from 
             outside applications.  Be sure to have recent backups of all
             files as a safeguard.


Backup Data Files

             On a regular, consistent basis, backups should be made of 
             Easy Project files.  This option will copy all databases 
             (.DBF) to a floppy disk.  If you are using a two floppy 
             system, use drive A:

             NOTE:  This function copies only data files.  Regular backups 
             of all Easy Project files should be made using the DOS COPY or 
             DISKCOPY commands.

             If files are used from a backup, be sure to reindex the 
             files.





                           E A S Y  P R O J E C T  (tm)



                         Utility Menu (continued)


Configure Monitor

             This option sets the proper type of monitor for your system.  
             To have these changes take effect, exit Easy Project 
             completely and then re-enter.


Configure Printer

             Easy Project supports many printers.  Find the number that 
             corresponds to your printer and enter the number at the 
             prompt.  If your printer is not listed, choose either the 
             I.B.M. Graphics or Other ASCII Printer.

             To print Gantt charts using the same graphic characters that
             are displayed, your printer must support the I.B.M. character 
             set.


Exit

This will return you to the Main Menu.





                       E A S Y  P R O J E C T  (tm)


                                Conclusion


     We hope this User Guide assists in your using Easy Project.

     Easy Project is a dynamic system that will constantly be upgraded
     and improved.  Your suggestions and comments are greatly appreciated.

     If you have any questions about Easy Project, please contact us
     by mail or via CompuServe EasyPlex.

     Please remember to register if you find yourself using Easy Project.
     Registered users will receive:

             1.  Latest version of Easy Project with Shareware screen
                 disabled

             2.  Printed User Guide with sample screens, reports and
                 Gantt charts 

             3.  Notification of updates

             4.  Free technical support

     Thanks again for using Easy Project.



                             Parcell Software
                           948 Manchester Course
                             Geneva, Il  60134
                              (312) 232-6328

                        CompuServe ID (72250,1356)