WorkQueue(tm) TUTORIAL


          This tutorial consists of this document plus the data files
          listed at the end of this section.

          It is assumed you have read the PRINTME.DOC document and
          installed WorkQueue on your PC.

          Each of the three lessons explores progressively more advanced
          features and capabilities and builds on the previous lesson.

          While exploring a lesson, you are encouraged to experiment -
          there are too many features in WorkQueue and too many ways to
          achieve results to be taught in a few pages.

          Also, learn to use the on-line help. It contains operating
          instructions for each screen and the entire user's guide with an
          index.

          The lessons are built around a single theme - you are the
          maintenance manager of a private school and are responsible for
          getting a dormitory of rooms painted within the summer break.

          The lessons teach you how to deal with both the expected and
          unexpected problems that arise while planning the work. It also
          shows you how to use WorkQueue to explore alternatives to find
          which one best meets the goal.

          The only convention you need to be aware of while taking the
          lessons is every place you need to enter keystrokes is marked
          with a >> .

          The following are files necessary to take this tutorial:

               LESSON1.RDC, LESSON1.PDC, LESSON1.WQP, LESSON2.RDC,
               LESSON2.PDC, LESSON2.WQP, LESSON3.RDC, LESSON3.PDC,
               LESSON3.WQP, HOLIDAY.HDC

          You will be allowed to change and save these files so keep a copy
          of the originals for others to use with this tutorial.


                                    1. LESSON ONE

          This section of the tutorial covers the basic aspects of
          WorkQueue including:

               Starting and stopping the system.



          Copyright 1989-1992 by Lane Davis                          Page 1






               How to use the action bar, menus, dialogue boxes and list
               boxes.

               How use the work plan, staff plan and holiday schedule to
               calculate a work schedule.

          Start WorkQueue by changing to the directory you keep the system
          files in and entering:

          >> WQ


          1.1  Choosing a Project

          The first thing you'll see is the opening screen that discusses
          Shareware and gives an overview of licensing terms. If this copy
          of WorkQueue is licensed, you won't see this information.

          You proceed past this screen by pressing any key.

          Next is displayed is a "dialogue box" asking for the name of the
          project you want to work on. Dialogue boxes are used throughout
          WorkQueue to get information about what you want to do next.

          >> Press F4 to display a list box of projects.

          WorkQueue uses list boxes for many functions and they all work
          the same:

               Use the PgDn or PgUp keys to scroll through the list.

               Press any alphabetic key to automatically scroll the list to
               the first item that starts with that letter. Press the
               letter again to move the bar to the next item that starts
               with that letter, etc.

               Use the up and down arrow keys to move the bar to your
               selection and press Enter.

          >> Choose the "LESSON1" project.

          The three data files will then be automatically filled in along
          with a description of the project:

               Work Plan                LESSON1.RDC
               Staff Plan               LESSON1.PDC
               Holiday Schedule         HOLIDAY.HDC

          >> Press the Enter key to continue.



          Copyright 1989-1992 by Lane Davis                          Page 2






          The "action bar" will appear across the top of the screen. This
          lists each of the actions you can take. Choosing an action will
          usually display a "drop-down" menu from which you choose an item,
          others will switch to a dialogue box to complete the action.

          You can make choices from either the action bar or a drop-down
          menu by:

               Moving the selection bar to your choice and pressing enter
               (use the arrow keys to move the bar).

               Each choice has a capital letter in it, you can activate
               that choice by pressing that letter on the keyboard (either
               upper or lower case).


          1.2  The Work Plan

          >> Press "v" to show the "view" menu.

          >> Press "w" to show the work plan.

          This work plan consists of only one job - to paint a dormitory
          full of rooms.

          >> Press F1 to review the operating instructions for Jobs and
          while you are in the help screen, also review the User's Guide
          for the Work Plan. When the help screen appears, notice there is
          a short "horizontal" menu with a choice bar at the bottom. You
          can select a category of help by using the left and right arrow
          keys to move the bar to a category and press enter to display it.
          The exception is the Index - you can only display it by pressing
          the F4 key. This is an index to the user's guide by subject and
          table of contents. When you are looking at a WorkQueue screen and
          press F1, the help screen shown next is for that screen. In other
          words, help is context sensitive. The index is provided when you
          need to review a subject "out of context".


          >> Press Escape to exit help.

          Note that the Job has a Target Date of 8/6. The school's Business
          Manager (your boss) has told you the new Freshmen will begin
          moving into the dormitory on that date. In other words, all
          painting must be finished by then.

          >> Place the cursor anywhere on the job and press Enter to show
          the Tasks for that Job.

          There are 18 tasks, one for each room.


          Copyright 1989-1992 by Lane Davis                          Page 3






          Notice that only the Job Number, Task Number, Task descriptions,
          Skill and Remaining Workdays (REM W/D) are filled in. These are
          generally the only data elements needed to create a task where
          the work can proceed at whatever pace the staff can support. This
          type of work is called "staff driven" - for a description of the
          other work types that can be used, look at the User's Guide.

          >> Press F1 to review the operating instructions for Tasks and
          while you are in the on-line help, review the User's Guide and
          Glossary.


          1.3  The Staff Plan

          >> Press Esc(ape) to return to the Job Screen.

          >> Press Esc again to "pop-up" the menus.

          >> Press "v" to "pull down" the View menu.

          >> Press "t" to view the Staff Plan.

          There is only one person available to paint the rooms and he has
          one skill - "PAI" for "PAINTING". The skill could have been named
          any 1-3 letters as long as it meant "painting".

          >> Place the cursor anywhere on the person and press Enter to
          show the Time Records. There is only one time record for this
          person:

               A "base rate" that says that person is available 5 days per
               week.

          >> Press F1 to review the operating instructions and user's guide
          for Time Records.


          1.4  The Holiday Schedule

          >> Press Esc to return to the Person Screen and Esc again to show
          the menus.

          >> Press "v" to display the view menu and "d" to display the
          Holiday Schedule.

          >> Press F1 to review the operating instructions and user's
          guide.





          Copyright 1989-1992 by Lane Davis                          Page 4






          1.5  The Work Schedule

          >> Press Esc to activate the menus, "s" to display the schedule
          menu and "c" to compute a schedule.

          The next thing you'll see is the Work Scheduling dialogue box.
          From here you can choose the duration of the schedule to be
          computed and the date to start from.

          >> Press F1 to review the operating instructions.

          >> Key in "7/1/91" for the start date and "1" for the duration,
          then press Enter to proceed (this lesson was designed to use this
          date and duration - you could have used any other).

          The next screen is the Work Schedule (job level) - it shows the
          duration of each job - only one in this case.


          >> Press F1 to review the operating instructions and user's
          guide.

          Note the following:

               Work started the week of 7/1 and finished the week of 8/8.

               In the first week (7/1) only three days of work were
               scheduled because the Independence Day holiday is both the
               4th and 5th.

               In the last week, 0.4 days of work were scheduled because
               that was all the work need to finish the job.

               In the 4 weeks between, 5 days of work were scheduled each
               week.

               The target date shows on the schedule as a "t".

          This adds up 23.4 work days. The total number of workdays
          scheduled will always be the number of workdays in the work plan
          unless there is work that couldn't be scheduled.

          >> Place the cursor on the job and press Enter.

          This will show the schedule for the Tasks contained in the job.

          >> Press F1 to review the operating instructions and user's
          guide.




          Copyright 1989-1992 by Lane Davis                          Page 5






                                    2. LESSON TWO

          >> Return to the main menu (by pressing Esc until the menus
          appear).

          >> Press "f" and then "c" to change to another project (lesson).

          Choose the project named "LESSON2".


          2.1  Not-Before Date

          You have just been told that room number 11 will not be vacated
          until 7/10.

          To see how this affects the schedule, view the work plan and
          bring the task for painting room number 11 up on the screen.

          Add a Not-Before date of 7/10/91.

          Compute a new schedule with the same start date and duration as
          before. Note that the work will still be done by 8/5 so you can
          still finish the work on time. It simply means that room number
          11 won't be done first.


          2.2  Vacation

          Jerry (you're only painter) just told you his son is getting
          married on 7/17 and he needs 5 days vacation starting 7/15 to
          attend the wedding.

          View the Staff Plan and bring Jerry's Time Records up on the
          screen.

          You need to add a new time record to describe Jerry's vacation.
          Read the operating instructions (F1) to find out how.

          The new Time Record should contain:

               Start Date:    7/15/91
               Stop Date:     7/19/91
               Work Rate:     0.0
               Description:   Vacation

          Re-compute the schedule. Bad news - you can't make the target
          date based on the current staff and work plans (work is not
          completed until 8/9). Also, note that there were 1.3 days of work
          (room number 36) that couldn't be completed.



          Copyright 1989-1992 by Lane Davis                          Page 6






          The reason for the incomplete work is Jerry is available to paint
          only until 8/9 - he must begin painting the Headmaster's house
          after that, a job that cannot be postponed.


          2.3  Overtime

          Since changing the target date would be very difficult, if not
          impossible, there are only three options:

               Tell Jerry he can't attend his son's wedding.

               Pay Jerry to work enough overtime to finish on schedule.

               Hire an additional painter.

          You don't consider the first option reasonable and, considering
          that hiring a new painter might take awhile, you decide to use
          overtime to make the target date.

          The question is - how much overtime? Does it need to be before
          the wedding or can it wait until after?

          To answer these questions, Add another time record for Jerry (in
          the staff plan) and give it the following data:

               Start Date:    7/22/91
               Stop Date:     8/5/91
               Work Rate:     2.0
               Description:   Overtime

          This starts the overtime after the wedding. When you re-compute
          the schedule, it yields a completion date of 8/6 - barely in
          time. This also means if anything else goes wrong, the target
          date is once again in jeopardy but you decide to go with this
          plan anyway.



                                   3. LESSON THREE

          Load the project named "LESSON3"

          You have just found out that a plumbing leak occurred on the
          third floor of the dormitory in room 36 and repairs will be
          needed on the second floor, to room 26, since the water leaked
          down through the walls and ruined the plaster (this is an old
          dormitory).




          Copyright 1989-1992 by Lane Davis                          Page 7






          3.1  Networking

          To accurately represent this delay, you will have to add a task
          for the repairs in room 26 and "network" it with the task to
          paint room 26. In networking jargon, this means making the
          painting task "dependent" on the repair task.

          First, add a task for the room repairs. The most logical place to
          put the task is just before the painting task. Display the tasks
          on the screen and move the cursor to the task for painting room
          number 26.

          >> Press Alt+I (a lower-case "i" is ok) to insert a new task just
          before the task for room number 26.

          The new task will be empty except for the Job and Task Numbers.
          To complete the task, key in the following information:

               Description:             Repairs to 26
               Remaining Workdays:      3.0
               To Node:                 REP1

          (In order to key in the To Node, you will first need to scroll
          laterally by pressing the F9 key.)

          When you key anything into a Node (either From or To), that node
          is automatically created and can be referred to by any number of
          other tasks as a From or To node. The node name, in this case
          "REP1", can be any 1-4 characters you choose.

          To complete the networking, key the same node name (REP1) into
          the From Node of the painting Task.

          Recompute the schedule.

          PROBLEM: The Job Schedule screen shows unfinished work. To find
          out why, display the Task Schedule screen and then press F1 to
          interpret the problem codes on the right side of the screen.

          It turns out there are two problems:

               A.   The repair task couldn't be started because there is no
                    one with plumbing skills in the staff plan.

               B.   Since the repair task wasn't finished, the painting
                    task for room 26 couldn't be started because you
                    "networked" the two (you made starting the paining task
                    dependent on the completion of the repairs).




          Copyright 1989-1992 by Lane Davis                          Page 8






          To fix this, add a plumber to the staff plan:

               Initials:      MP
               Name:          Mister Plumber
               Skill1:        PLU

          Don't forget to add a time record:

               Start Date:    8/2/91
               Stop Date:     8/7/91
               Work Rate:     5.0
               Description:   (leave blank - not needed).

          Now re-compute the schedule.

          Now all the work is being completed but you're 2 days behind
          schedule. In this case, you are unable to get another plumber any
          earlier so you choose to write a letter to the two students
          scheduled to move into room 26 to tell them not to arrive until
          August 9th.


                                 4. FURTHER "STUDY"

          The remaining WorkQueue facilities can be explored by
          experimentation and reading the on-line help. At a minimum,
          review the following:

               The "List" facility. On most screens there are data entry
               areas where, if you press F4, a list of alternatives is
               shown from which you can choose. For example, try it on a
               date element such as the Target Date in the Work Plan.

               Staff Utilization Staff Availability Analysis. These are
               menu items that help you improve the utilization of you
               staff and also help diagnose scheduling problems.

               Filtering - a menu item under "Options". Filters let you
               limit what you see on the screen or print in a report. This
               can be very useful, especially on a complex schedule. For
               example, you can display the work schedule for only one
               person.

               Reports - the best way to see what reports are available is
               to print them for one of the lessons.







          Copyright 1989-1992 by Lane Davis                          Page 9