������������������������������ͻ

� E A S Y  P R O J E C T  (tm) �

�         Version 3.0          �

�                              �

�         USER MANUAL          �

������������������������������ͼ

A Project Management and Tracking System

for the I.B.M. Personal Computer and Compatibles

(c) Copyright 1987, 1988 Parcell Software

All Rights Reserved

Parcell Software

P.O. Box 165

Geneva, Il  60134  U.S.A

(312) 232-6328

CompuServe ID:  72250,1356

���������Ŀ

���������Ŀ     �              (tm)

�ĳ         �o    �������������������

�   ���������Ŀ �  Association of

�   �         ���  Shareware

���ĳ    o    �    Professionals

�����ĳ    �    ���������������������

�����������    MEMBER

(c) Copyright 1987,1988  Parcell Software

All Rights Reserved Worldwide

Printed in the United States of America

Parcell Software

P.O. Box 165

Geneva, Il  60134  U.S.A.

Phone:  (312) 232-6328   (9:00 a.m. - 5:00 p.m. Central Time)

CompuServe:  72250,1356

Trademarks

Easy Project is a trademark of Parcell Software

I.B.M. is a registered trademark of the I.B.M Corporation.

dBASE III is a registered trademark of Ashton-Tate, Inc.

License Agreement

Easy Project is a Shareware program.  It is not free.

Easy Project is copyrighted software owned by Parcell Software.

Continued use requires a license registration fee of $49.00.

Registration covers use on one PC only.  Multiple copies of Easy

Project must be purchased for use on multiple PC's.  Quantity

discounts and site licenses available.

All licensed users receive:

-  Current version of Easy Project with Shareware screen

disabled

-  Printed, bound User Manual

-  Notification of updates

-  Free technical support

You are encouraged to copy and share this program with other users.

When sharing this program, all files and documentation must be

distributed without any alteration.  No fee can be charged for any

copying or distribution except for a nominal fee to defray expenses.

Disclaimer

Parcell Software specifically disclaims any warranty, either

expressed or implied, including but not limited to the

implied warranties of merchantability and fitness for a

particular use.

In no event shall Parcell Software be liable for any special,

consequential, or other damages, including loss of profit

arising out of the use of this program

Easy Project 3.0                                                Page 2

E A S Y  P R O J E C T  (tm)

Introduction

Easy Project is a project management tool for the I.B.M. and

compatible personal computers.  Easy Project is designed to be an

easy to learn, practical, and efficient method for planning,

tracking, and controlling all types of projects.  You, the

manager, plan the activities or tasks needed to complete the project

in a top/down outline fashion.  The Gantt chart then displays the

project graphically by using time bars which span the time

period of each task.

Easy Project features:

1.  User defined project phases (20 maximum)

2.  Unlimited number of resources per project

3.  User defined tasks (1000 per project)

4.  User defined subordinate tasks or items (100 per task)

5.  Fast data entry with multiple resource assignments

per task

6.  Automatic scheduling and schedule maintenance

7.  Gantt charts showing planned vs. actual dates

with variable scales

8.  Extensive reporting including work plans, status reports,

and earned value accrual reporting

9.  Online context sensitive help screens

10.  dBASE III file compatibility

Sample data is provided to assist in learning and using Easy

Project.

Easy Project 3.0                                                Page 3

System Requirements

Hardware

I.B.M. PC/XT/AT/PS2 or 100% Compatible with at least 380K RAM

Monitor

Any

Printer

Over 40 different printers are supported.  If your particular

printer is not listed on the configuration screen, please

contact us.

Software Requirements

DOS 2.x or 3.x

CONFIG.SYS File (sample is included)

A CONFIG.SYS file must be in the root directory of your

hard disk or on your boot DOS floppy.  This file must

contain the following two records:

BUFFERS = 15

FILES = 24

These values are minimum values.

Re-boot DOS after making these changes.

First Time Installation

Hard Disk

1.  Make a backup or working copy of your Easy Project disk

2.  Place your working copy in drive A and type:

INSTALLH <enter>

This installation procedure will create a sub-directory on

your hard disk of \EP and copy the necessary files.

NOTE:  This process assumes drive C is your hard disk.  If this

not the case, edit the INSTALL.BAT file accordingly.

2 Floppy System

1.  Make a backup of your Easy Project disk.

2.  Using backup copy in drive A and a blank formatted disk

in drive B, type:  INSTALLF <enter>

This process will copy all necessary data files to drive

B and keep system files on drive A.  Label the disk in

drive A "EP System" and the disk in drive B "EP Data".

Easy Project 3.0                                               Page 4

Upgrading Prior Versions

To install version 3.0 of Easy Project if you've already been using a

prior release, follow these steps:

1.  Backup all current Easy Project files

2.  RENAME EPPROJ.DBF EP2PROJ.DBF

RENAME EPPLAN.DBF EP2PLAN.DBF

RENAME EPRES.DBF  EP2RES.DBF

3.  Copy all 3.0 files to floppy or hard disk

4.  COPY EP2RES.DBF EPRES.DBF

5.  Start Easy Project (EP)

6.  Choose Utilities option and Reindex Files

7.  Choose Utilities option and Configure System

8.  Choose Utilities option and Convert 2.0 Files

Starting Easy Project

Hard Disk

From the \EP directory, type:  EP <enter>

2 Floppy System

With the EP System disk in drive A, the EP Data disk

in drive B, and drive B as the default drive,

type :  EP <enter>

NOTE:  The first time you execute Easy Project, choose the

Utilities option from the Main Menu.  From this menu,

configure both your monitor and your printer.  After

making your choices, exit the system and re-enter to

have the monitor configuration take effect.

Start-up Error Messages

1.  DOS Error 2 - One or more files is missing from your

installed system.  Please check your

original disk.

2.  DOS Error 4 - Too many files are open.  Check your

CONFIG.SYS file (see Software Requirements).

Easy Project 3.0                                               Page 5

Data Entry Notes

On all Easy Project data entry screens, the cursor can be

controlled in the following fashion:

Key                         Result

<��   (Enter)          Proceeds to the next field.  When

pressed while the cursor is in the

last field of a screen, all data

will be saved.

PgDn                   Exits the screen saving all changes.

Esc                    Exits the screen without saving any

changes.

Up Arrow               Moves cursor to previous field.

Down Arrow             Moves cursor to next field.

<-                     Moves cursor backward one space.

->                    Moves cursor forward one space.

F1                     At any time while in Easy Project,

help is available by pressing 'F1'.

Easy Project will recognize what field

or menu the request came from, and

then display the appropriate text.

F5                     Deletes record while in Resource or

Task update screens.

Three heavily used fields will provide additional HELP when F1 is

pressed:

Project Number:  Will list all current projects on file.

Task Number:     Will list all tasks for a particular

project.

Resource:        Will list all resources for a

particular project.

Easy Project 3.0                                               Page 6

Main Menu

The Main Menu is the driver for Easy Project.  The desired option

can be chosen using either one of two methods:

1.  Use the left/right arrow and highlight the desired

option and then press <Enter>

2.  Press the capitalized letter of the desired choice

(i.e. T=Task, O=repOrt)

The components of the Main Menu are:

Project

Create project numbers, project descriptions,

phase descriptions and define holidays

Resource

Maintain resource data

Task

Maintain task data

Quick-input

Mass input for new tasks

Schedule

Schedule work plans automatically

Gantt

Produce Gantt charts for a project detailing

planned vs. actual progress

repOrts

Generate many different reports including work plans,

status reports and summary reports

Utilities

Configures system and provides sundry utility

file handling

License

Print license and registration form

Exit

Return to DOS

Easy Project 3.0                                               Page 7

Creating a New Project

Easy Project is designed for quick project creation.  After

spending a short time entering project data, Gantt charts and

reports will become available.

Follow this process when creating a new project:

1.  Choose 'Project' from the Main Menu and enter a project

number, descriptions, phase descriptions and

project holidays.

2.  Choose 'Resource' from the Main Menu and

add resource data for the project.  Resources will be

identified by assigning them a unique user defined code.

3.  Choose 'Task' from the Main Menu to enter and maintain

tasks to the project. (See Notes On Entering Tasks)

4.  If you want Easy Project to calculate estimated schedule

dates, choose 'Schedule' from the Main Menu. (See Notes on

Automatic Scheduling)

5.  At this point, Gantt charts and/or reports may be produced.

NOTE:  A sample project has already been established.  Use the

project code of "EASY" (all caps) to view this project.

Editing an Existing Project

When initially starting the system, no project will be active.  To

activate or retrieve a project, you will be prompted for the project

number the first time you try any Main Menu function - except Gantt.

To change projects, go to the 'PROJECT' screen or any report

screen.

Easy Project 3.0                                               Page 8

Set Up Project Parameters

Easy Project has the ability to store data from several different

projects at one time.  Each of those projects may have different

base parameters.

Before entering task or resource data for a particular project,

certain parameters or criteria must be defined.

Project Number

Every project must have its own unique project number.  This

number is used to tell the system what project should be

retrieved or added.  This number can be composed of any

combination of characters or numbers (5 character maximum).

NOTE:  Pressing 'F1' while on the project number field will

provide a list of all active projects.

Project Name

The Project Name is used to identify the project.  This

description will appear on all screens and reports.

Project Description

To further define a project, use these fields.  The data

entered here will print on all reports.

Phase Descriptions

For most projects, it is better to divide the project into

smaller, more manageable phases.  An example of phases could

be:

1.  Lay foundation

2.  Framing

3.  Plumbing

Easy Project permits 20 different phases to be defined for

one particular project.  The descriptions entered here will

appear on project summary reports.

Non-Schedule Days

Twelve different dates may be entered as non-schedule days.

These will be useful in scheduling holidays and/or vacations.

Weekends?

If weekends are not to be used when scheduling, enter a 'N'.

If weekends are to be scheduled, enter a 'Y'.

Easy Project 3.0                                               Page 9

Resource Maintenance

Before tasks can be entered, resource information must be

established.  Resources consist of people (employees, consultants,

etc.) or fixed type (materials, capital expenses, etc.).

Field Descriptions

Code:        Each resource must be assigned a unique

identifier.  This identifier could be a name,

initials or an account code.  The identifier

can be up to 6 characters and is alphanumeric.

NOTE:  Pressing F1 while the cursor is on the

code field, will produce a display

of all resources assigned to

this project.

Name:        Enter the full name or description of the

resource.

Rate:        The charge rate for the resource. (optional)

Type:        Choose either Hourly, Daily, or Fixed.

Dept:        Enter a department code for the resource.  This

code may be up to 3 characters and is

alphanumeric.

NOTE:  This is an optional entry but is required

to produce departmentalized reports.

Useage:      Use to identify how many hours this resource

works in one day.  (not needed for Fixed types)

Example:  8 = 8 hours/day

4 = 4 hours/day (part time)

Source:      An optional entry to further describe the

resource.

Example:  EMP = Employee

CON = Consultant

Note 1 &

Note 2:      An optional entry to use for any purpose.

Easy Project 3.0                                              Page 10

Task Maintenance

Task definition is the heart of project management.  Easy Project

permits for practical task creation and maintenance.  Before sitting

down and entering data, plan what logical order your tasks will

follow and if possible, divide your project into phases.  Once your

data has been entered, refinement and maintenance is easy.

Field Definitions

Task:                  Enter the two digit phase number plus

four digit task number for this task.

Refer to 'Notes on Entering Tasks' for

choosing task numbers.

Item:                  Each task can consist of numerous

subordinate tasks or items.  Enter an

item number in this field. (optional)

Network:               Large projects may have different

phases running concurrently.  Use this

to designate to which network or node

this task belongs to.  For most

projects, use the phase number. (The

default value is the phase number)

Successor:             Use this field to define task

dependencies. Refer to 'Assigning

Successors'.

Description:           Enter the description for this task.

This description will appear on all

reports and Gantt charts.

Milestone:             Milestones reflect major project

accomplishments.  If this task is

considered a milestone in the project,

enter a 'Y'.

Resource:              Enter the resource code of the

resource assigned to this task.  A

maximum of four different resources

may be assigned to a particular task.

Est. Time:             Enter the amount of time (hours/days)

expected to take to complete this task.

Time To-Date:          Enter the amount of time this resource

has taken thus far for this task.

New Est:               Enter the revised time estimate to

complete this task.

Easy Project 3.0                                              Page 11

Task Maintenance (continued)

Planned Start/Stop:    Enter the original or planned start

and stop date for this task.

Actual Start/Stop:     Enter the current start and stop date

for this task.

Fixed Date:            Enter a 'Y' if the dates associated with

this task cannot be changed for any

reason.  This is useful for vacation

use.

Status:                This will designate the status for

this task.  When completed, use a

'C'.

Note 1 & Note 2:       To be used for any purpose.

Easy Project 3.0                                              Page 12

Notes on Entering Tasks

Every task number consists of the following elements:

Task Number  - 2 character phase number (01-20) plus

4 character task number (user defined)

Item Number  - 2 characters, user defined (optional)

Successor    - 8 characters, made up of (Phase + Task +

Item)

Keep in mind that most reports are produced in task number order.

Using sequential task numbers of 001, 002, etc. within each phase is

recommended.

'Item' is meant as a subordinate task.  This is an optional entry

but is useful in breaking down a large main task.  Again, it's

useful to use sequential item numbers within each task number.

'Successor' designates what task, if any, cannot start until the

current task is completed.  This is optional and if not needed will

default to its own task and item number.  If this is used, it should

consist of the phase, task and item number of the succeeding task.

Assigning Successors

If the task following the current task cannot begin until the

current task is complete, enter the succeeding task number in the

successor field of the current task.

Example:  A phase has 4 tasks, 0001 thru 0004.  Every task

is dependent upon the previous task.  The tasks

should be established as follows:

Task              Successor

01-0001            01-0002

01-0002            01-0003

01-0003            01-0004

01-0004            01-0004

If tasks can run concurrent with each other, set up the tasks in

this manner:

Task              Successor

01-0001            01-0002

01-0002            01-0002 --

01-0003            01-0003   | Concurrent Tasks

01-0004            01-0005 --

01-0005            01-0005

Easy Project 3.0                                              Page 13

Sample Task Numbers

Task Field  =  01-0001

Item Field  =  01

Successor   =  01-0002 01

Explanation:  This task belongs to Phase 1, Task equals 0001 and

this is the first item for task 0001.

Task/Item 01-0002-01 cannot start until this task

is complete.  01-0002-01 is placed in the

'Successor' field.

Task Field  = 01-0003

Item Field  =

Successor   = 01-0003

Explanation:  This task belongs to Phase 1, Task equals 0003 and

there are no subordinate items.

No other task is dependent upon this task so the

'Successor' field defaults to itself.

Quick-Input

To add tasks to a project in a simple and fast method, try this

option.  The 'Quick-Input' option will permit 19 tasks to be entered

from one screen.  The following limitations currently exist when

using this screen:

- Planned or actual dates cannot be entered

- Milestone, Fixed Dates, Notes or Status fields

cannot be entered

- The estimated time entered is applied to Resource 1

This screen is new and will change in its features.  Any ideas?

Please contact us with any suggestions you might have.

Easy Project 3.0                                              Page 14

Automatic Schedule Maintenance

If a planned start or stop date is changed, for an existing

task, the automatic scheduler will be invoked adjusting both

planned and actual start/stop dates for the following tasks.

You will have the ability to override the proposed dates.

Likewise, if a current start or stop date is changed, the

automatic scheduler will be invoked to adjust current dates

only.

Marking Tasks Complete

For the purpose of the Project Status Report and the Gantt

chart, a status of 'C' denotes that a task is complete.

Easy Project 3.0                                              Page 15

Automatic Schedule Generation

Easy Project will automatically calculate planned start and stop

dates based on the estimated time assigned to each task.

To calculate dates, enter the project number followed by the base

start date.  The base start date should be the date the project may

begin.

Schedule Screen Display

As the schedule generates, each task and the newly calculated dates

are displayed.  After the screen fills, you have the ability to

change or override the calculated date.  Pressing <ESC> aborts

the update process and the records will not be updated.

Use the <ENTER> key to advance the cursor.  When the screen

is completely updated, these dates will be used to update both the

planned and the actual start and stop dates for the tasks.

Notes on Scheduling

1.  In the case of multiple resource tasks, the resource

taking the greatest amount of time will be used in

calculating the schedule. (the display reflects this)

2.  Any task which has a fixed type resource will be ignored.

3.  On the Resource update screen, the Useage field should

reflect the total number of hours the resource works

in one day. Use this for both hourly and daily type

resources.

4.  Weekends will be taken into consideration when

calculating the schedule based on the option chosen

from the Project Parameter screen.

5.  If a task was set up with the Fixed Date option set,

the task date will be used instead of the calculated

date.

Calculate Critical Path Only

In the case of projects with concurrent phases, you may want

to calculate the critical path of the project.  The critical

path will be the longest phase or network in time duration.

Setting this option to 'Y' will not calculate any new dates.

Easy Project 3.0                                              Page 16

Schedule Networks Parallel

If this option is set to 'Y', each phase or network will be

scheduled from the project start date.  This permits multiple

phases to be scheduled at the same time.

Easy Project 3.0                                              Page 17

Gantt Chart Parameters

Easy Project's Gantt charts are designed to give a graphic display

of a projects planned vs. actual progress.

Two different types of charts may be produced:

1.  A chart displaying tasks for one particular phase in

task number order.

2.  A chart displaying the entire project with tasks grouped

by dependencies.

In order for a task to be displayed, it must have a Planned Start

Date.

Scale Options

Flexible Gantt scales can be chosen to insure the most complete view

of a project.  Each symbol on the chart can represent from 1 to 6

days or weeks.  For projects of short duration, a scale in days is

probably more appropriate.

Output Options

Easy Project offers three options for generating Gantt charts:

1.  (D)isplay - The chart will be displayed on your monitor.

If the scale is set to 1 day, a view of

2 months will be displayed.

2.  (P)rint - The chart will be printed in compressed format.

With a scale set to 1 day, a view of approximately

4 months will be printed.

3.  (F)ile -  The chart will be written to a disk file using the

default file name of GANTT.PRN.  This is an ASCII

text file that may be printed thru DOS or another

print utility.  If the scale is set to 1 day, a

view of approximately 6 months will be printed.

Gantt Chart Symbols

�   Planned Date

#   Actual Date

*   Completed Task

M   Milestone

@   Critical Task

<-  Task has start date prior to beginning of scale

Easy Project 3.0                                               Page 18

Report Menu

Many helpful reports can be instantly displayed, printed or written

to a disk file for later editing by your favorite word processor.

Due to space limitations, some reports are printed in compressed

format - thus giving more detail than when displayed.  The actual

title of each report is enclosed in ( ).

(A) Work Plan By Task (Phase Work Plan) - Produces a detailed

work plan for a particular phase in task number order.

[compressed]

(B) Work Plan By Resource (Phase Work Plan) - Produces a

detailed work plan for the entire project by grouping all

resources together. [compressed]

(C) Work Plan Project Summary (Project Work Plan Summary) -

Summarizes all phases of a project plan giving a concise

report.

(D) Work Plan Resource Summary (Project Resource Summary) -

Produces a departmentalized resource summary either for a

particular phase or the entire project.

(E) Project Status Report - Plan vs. Actual (Project Status

Report) - A to-date status report for the entire project

detailing variances.

(F) Project Status Summary - Actual (Project Work Plan

Summary) - Summarizes all project  phases showing actual costs

and current schedule dates. [compressed]

(G) Project Resource Summary - Actual (Project Resource

Summary) - Shows departmental break down of actual costs by

individual resource.

(H) Earned Value Report - A to-date report detailing project

cost accruals. [compressed]

Easy Project 3.0                                              Page 19

Report Menu (continued)

(I) Resource List (Project Resource List) - A detailed list

of all resources   assigned to a particular project.

NOTE:  Remember that Easy Project files are dBASE compatible and

can be read directly by many other applications.  It is possible to

create your own custom reports either by exporting the files or

using one of the above reports, using the 'F' (File) option, and

editing the ASCII file that is produced.

Easy Project 3.0                                             Page 20

Utility Menu

The Utility Menu consists of various functions that may be used for

file handling or system configuration.

NOTE:  Be sure to backup all Easy Project files on a regular basis.

This will help in recovering from any potential disasters.

(A) Reindex All Files

Easy Project uses index files which permit fast data

retrieval.  These index files are not compatible with dBASE.

All files with the extension of .NTX should never be deleted.

If file integrity is ever in question, choose the reindex

option.  File integrity may degrade due to abnormal

termination of the system.

It can never hurt the system to reindex files.

(B) Delete (Pack) Marked Records

When task or resource data is deleted using the 'F5' key, the

records are actually marked for deletion but physically remain

on file.  These records are unavailable for normal use.

The delete option on this menu will physically delete all

marked records.  Once this option is exercised, the marked

records can no longer be used or recovered.

(C) Undelete (Recall) Records

This option will find all records that have been marked for

deletion (and not packed), and recall or make them available

again for processing.

NOTE:  This option will recall all records from all projects

from all files regardless of project number.

(D) Delete Project

This function will delete all tasks, resources and related

records for a particular project.

To use, first enter the project number to delete.  Next, you

will be prompted to verify that you really want to delete the

project.  Answering 'N' will bypass any deletions.  If

verified, records are marked for deletion.

Easy Project 3.0                                              Page 21

Utility Menu (continued)

(E) Copy or Clone Project

On occasion, you may want to create a project that has many

similar tasks as another previous project. The copy option

will take a current project and duplicate all tasks and

resources using a new project number.  The old project remains

intact with no changes.

(F) Copy or Clone Resources

On occasion, you may want to create a project that has many

similar resources as another previous project. The copy option

will take current resources from one project and duplicate

them using a new project number.  The old project remains

intact with no changes.

(G) Rebuild Files from Importing

Easy Project database files (.DBF) are dBASE III compatible

and can be exported directly into many other applications.

Exporting may provide useful for additional reporting or mass

updating.

If files are exported and updated outside of Easy Project,

they must be rebuilt.  This function will automatically

rebuild index files and all necessary relations.

NOTE:  Exercise caution when updating Easy Project files from

outside applications.  Be sure to have recent backups of all

files as a safeguard.

(H) Backup Data Files

On a regular, consistent basis, backups should be made of

Easy Project files.  This option will copy all databases

(.DBF) to a floppy disk.  If you are using a two floppy

system, use drive A as the target or destination drive.

NOTE:  This function copies only data (.DBF) files.  Regular

backups of all Easy Project files should be made using the DOS

COPY or DISKCOPY commands.

If files are used from a backup, be sure to use the 'Rebuild'

option to maintain file integrity.

Easy Project 3.0                                              Page 22

Utility Menu (continued)

(I) Configure System

This option sets the proper type of monitor for your system

and the proper destination for printer output.  To have these

changes take effect, exit Easy Project completely and then

re-enter.

(J) Configure Printer

Easy Project supports many printers.  Find the number that

corresponds to your printer and enter the number at the

prompt.  If your printer is not listed, try either the I.B.M.

Graphics or Other ASCII Printer.

Easy Project 3.0                                              Page 23

Conclusion

Easy Project is a dynamic system that will constantly be upgraded

and improved.  Your suggestions and comments are greatly appreciated.

If you have any questions about Easy Project, please contact us

by mail, phone or via CompuServe EasyPlex.

Please remember to register if you find yourself using Easy Project.

Licensed users will receive:

1.  Latest version of Easy Project with Shareware screen

disabled

2.  Printed User Manual with sample screens, reports and

Gantt charts

3.  Notification of updates

4.  Free technical support

Thanks again for using Easy Project.

Parcell Software

P.O. Box 165

Geneva, Il  60134

(312) 232-6328

CompuServe ID: 72250,1356

Easy Project 3.0                                              Page 24

E A S Y  P R O J E C T

3.0

Registration Form

The license fee for Easy Project is $49.00 (U.S. funds only).  The

license covers use on one PC only.  Multiple copies must be purchased

for use on multiple PC's.  Quantity discounts and site licenses are

available.  Contact us for further information.

Method of Payment:

Personal Check

Purchase Order (Government, Schools, Fortune 1000)

VISA       --|

|  Phone order accepted:  (312) 232-6328

Mastercard --|

Card Number:

Expiration Date:

Name on Card:

Phone Number:

Signature:

SHIP TO:

Name:                                              Date:

Title:

Address:

Where did you hear about Easy Project:

Quantity| Description       | Unit Cost   |  Total Cost

----------------------------------------------------------

| Easy Project 3.0  |   49.00     |              |

----------------------------------------------------------

Shipping (outside U.S.A. only)   5.00     |              |

----------------------------------------------------------

Total Payment:                  |              |

----------------

Mail Payment to:

Parcell Software

P.O. Box 165

Geneva, Il  60134