MainLine
               Project Management Software
               Revision 2.0




               By

               Minuteman Systems
               P.O. Box 152
               Belmont MA  02178









          Preface

          Copyright Information

          Copyright 1992, 1993, 1994 by Minuteman Systems

          The software and the disks on which it is contained are
          licensed to you, for your own use. This is copyrighted
          software. You are not obtaining title to the software or any
          copyright rights. You may not sublicense, rent, lease,
          convey, modify, translate, convert to any other programming
          language, decompile, or disassemble the software for any
          purpose.

          You may make as many copies of this software as you need for
          backup purposes. You may use this software on more than one
          computer, provided there is no chance it will be used
          simultaneously on more than one computer.



          Registration Information

          This program is supplied as Shareware. This means that you
          may evaluate the program for free, but are required to pay a
          registration fee if you keep it and use it.

          Note that any fee paid to a Shareware distribution company
          or similar supplier does not replace, nor contribute
          towards, the registration fee.

          If you are satisfied with the program and wish to use it,
          you may register it by filling out a hardcopy of the
          included file ORDER.TXT. Send it with a check or money order
          for $29.95 to
          Minuteman Systems, PO Box 152, Belmont, Massachusetts,
          02178. As a registered user, you will receive

          o  A printed, bound User's Manual.
          o  Free updates for one year.
          o  Telephone service.
          o  A personalized diskette with your name and a serial
             number. Also, the registration screen usually presented
             when exiting the program will be disabled.

          Incentive Plan - Once you have registered, have
          acquaintances list your name as a reference when they
          register. You will receive a $5.00 rebate.




          Notice

          This software is supplied as-is. There are no warranties,
          expressed or implied.

          Minuteman Systems disclaims all warranties relating to this
          software, whether expressed or implied, including but not
          limited to any implied warranties of merchantability and
          fitness for a particular purpose, and all such warranties
          are expressly and specifically disclaimed. Neither Minuteman
          Systems nor anyone else who has been involved in the
          creation, production, or delivery of this software shall be
          liable for any indirect, consequential, or incidental
          damages arising out of the use or inability to use such
          software even if Minuteman Systems has been advised of the
          possibility of such damages or claims. In no event shall
          Minuteman Systems' liability for any damage ever exceed the
          price paid for the license to use the software, regardless
          of the form of claim. The person using the software bears
          all risk as to the quality and performance of the software.

          Some states do not allow the exclusion of the limit of
          liability for consequential or incidental damages, so the
          above limitation may not apply to you.

          This agreement shall be governed by the laws of the
          Commonwealth of Massachusetts and shall inure to the benefit
          of Minuteman Systems and any successors, administrators,
          heirs and assigns. Any action or proceeding brought by
          either party against the other shall be brought only in a
          STATE or FEDERAL COURT of competent jurisdiction located in
          Middlesex County, Massachusetts. The parties hereby consent
          to in personam jurisdiction of said courts.



          Table of Contents
          Preface                                                  i
          1 Introduction                                           1
               1.1  How This Manual Is Organized                   1
          2  Installation                                          2
               2.1  System Considerations                          2
               Installation Procedure                              3
          3  Trial Run - 1st Pass                                  4
               3.1  The Initial Screen                             4
               3.2  Moving Around - Key Commands                   6
               3.3  The Command Menu                               7
               3.4  Quick Entry - Adding a Task                    8
               3.5  Storing a Project                              10
               3.6  Printing Reports                               10
               3.7  Exiting                                        10
               3.8  Examining The Reports                          11
          4  Trial Run - 2nd Pass                                  14
               4.1  Reading In A Project                           14
               4.2  Editing an Existing Task                       14
               4.3  Inserting, Deleting, Moving Lines              15
               4.4  Deleting A Task                                18
               4.5  Adding Descriptions to Groups of Tasks         19
               4.6  Adding A Date and Labels to The Display        19
               4.7  Multiple Editing Views                         22
               4.8  Locating Tasks - The "Search" Function         22
               4.9  The Wait Function                              23
               4.10  Changing Program Configuration                24
          5  Advanced Topics                                       28
               5.1  System Capabilities                            28
               5.2  Following The Critical Path                    28
               5.3  The Journal File - Recovering Damaged Project
               Files                                               28
               5.4  Attaching Fixed Dates to Tasks or  Milestones  29
               5.5  Project Rollups                                29
               5.6  Renumbering Tasks and Milestones               31
               5.7  Copying A Group of Projects                    31
               5.8  Importing Projects                             32
          6  Command Listing                                       33
               6.1  Filing                                         33
               6.2  Edit                                           33
               6.3  Search                                         33
               6.4  Display                                        34
               6.5  Print                                          34
          APPENDIX  A - QUICK-START INFORMATION                    1
               A.1  Starting Up                                    1
               A.2  Moving Around The Screen                       1
               A.3  Calling Up Commands                            1
               A.4  Basics of Editing and Generating Reports       2
               A.5  Notes on Dates and Calculations                2
          APPENDIX  B - SELECTING OUTPUT FORMATS                   1
          APPENDIX  C - SERVICE                                    1




          List Of Figures

               Figure 1: Blank Project                             5
               Figure 2: 1 Task Added                              9
               Figure 3: DEMO.DAT                                  12
               Figure 4: DEMO.RPT                                  13
               Figure 5: Tasks Added                               16
               Figure 6: Moved Lines                               17
               Figure 7: Adding Comments                           20
               Figure 8: Date and Label Fields                     21
               Figure 9: Using The Task Wait Function              23
               Figure 10: Display Options Configuration Menu       25
               Figure 11: Using Rollup Tasks                       30

                                                          1
     

          1 Introduction

          The principal job of the MainLine Project Management Program
          is to develop a schedule in a clear and understandable
          format, for the purposes of

          1. Identifying the parts of the project and their
             interdependencies.
          2. Allowing easy changes to the schedule for "what if"
             purposes.
          3. Providing compact reports suitable for presentations, and
             compatible with electronic mail systems for distribution
             to those working on the project.




          1.1  How This Manual Is Organized

          Section 2 describes the method for installing the program on
          the machine. It also discusses the requirements of the
          computer this program is to run on.

          Section 3 and Section 4 illustrate how to use MainLine by
          means of a series of examples.

          Section 3 goes over the basics - turning on the program,
          creating a simple project, and generating some reports.

          Section 4 demonstrates with further examples how to edit a
          project and manipulate the display of a project on the
          screen.

          Section 5 describes some advanced features.

          Section 6 lists all the individual commands available and
          describes each briefly.

          Appendix A includes "quick-start" information if you wish to
          get up-and-running prior to having read this whole manual.

          Appendix B gives further information on formatting the
          schedule output for printing and electronic mailing.



                                                          2


          2  Installation

          To install and use this program, all that is required is
          familiarity with the basics of DOS operation. If you aren't
          experienced with creating directories and copying files,
          consult the DOS documentation with your system.

           2.1  System Considerations

          This program is intended to be run on IBM-style personal
          computers and exact compatibles. The program has been
          successfully tested and used on numerous machines.

          This is a DOS program. It can also be called from Windows.

          Speed of the program will vary depending on the model of PC
          used. The program has been tested on 20MHz 386-SX machines
          and found to have very usable speed. It has been tested on
          older machines including 8 MHz "XT" machines - while the
          performance is slower, it is still quite usable.

          Whatever machine used should have at least 640K of RAM
          memory available.

          Note - The presence on a system of Terminate-And-Stay-
          Resident programs (TSRs), memory managers, or Local Area
          Network (LAN) software may interfere with the operation of
          this program. "Interference" usually  means that the program
          cannot load and execute. However, in borderline cases there
          may be misoperations during the running of the program. This
          includes things like running out of memory, or disturbances
          of the display. If you are experiencing difficulty loading
          or running this program, and any of those other types of
          software are installed on your system, try removing them or
          disabling them in various combinations to determine what is
          causing the problem.

          Video Considerations - The first time the program is used,
          it will default to run in a black and white mode compatible
          with most if not all video cards and display monitors
          available. The program's command menu has options for
          selecting the colors displayed, and for changing the
          resolution of the display. (See Section 4.9.) These
          selections may then be stored away as defaults for future
          use.


                                                          3

          Installation Procedure

          Registered users receive a diskette containing the updated,
          executable code and related files in non-compressed format.
          They should be copied directly into the existing working
          subdirectory on your hard disk.

          If the program is obtained from a Bulletin-Board-System
          (BBS), an electronic information system (i.e. CompuServe,
          Genie, Prodigy, America On-Line,  etc. etc), or the
          Internet, it will typically be presented as a single
          compressed file with a name like MAINLINE.ZIP, MAINLI.ZIP,
          or MNLIN2P0.ZIP. The file must be decompressed using a
          current version of PKUNZIP. The decompressed file will
          consist of the following files;

          o  ML.EXE - The executable program file.
          o  ML.ICO - An Icon file, for use under WIndows
          o  SMCGA.FNT - Fonts used in high resolution black/white
             display.
          o  SMVGA.FNT - Fonts used in high resolution color display.
          o  INSTALL.TXT - Notes about installing the program, similar
             to this section.
          o  ORDER.TXT - A Form for registering the program
          o  README.1ST - A brief description of the program,
             including installation considerations.
          o  PACKING.LST - A list of the included files.

          Create a subdirectory on your hard-drive such as C:\MAINLINE
          and copy the above files into it.

          Windows Installation: MainLine may be accessed from Windows.
          Create a program item for it under a new or existing program
          group. Attatch the ML.ICO icon file (f it does not happen
          automatically).

          The contents of diskettes obtained from Shareware vendors
          may vary but will typically include the following files;

          o  MAINLINE.EXE - A compressed, self-extracting file
             containing the executable code, this documentation, and
             several data files.
          o  INSTALL.BAT - Installation Batch File
          o  INSTALL.TXT - Instructions for using INSTALL.BAT to
             install the program.
          o  ORDER.TXT - A Form for registering the program
          o  README.1ST - A brief description of the program,
             including installation considerations.
          o  PACKING.LST - A list of the included files.

          Diskette vendors may also place other files on the diskette.

          Before doing any installation, it is best to make a backup
          copy of the supplied diskette. This is easily done by
          copying all files on the diskette using the DOS command;

          DISKCOPY b: b: (Assuming diskette drive is "b" - otherwise
          substitute the proper disk drive letter.)

                                                          4


           3  Trial Run - 1st Pass

          This section will go through the real basics - turning the
          program on, creating and saving a simple project, generating
          some reports, and exiting the program.

          First set the default drive to the one where you have stored
          the program. Start the program by entering ML followed by
          ENTER or Carriage Return (CR).


          3.1  The Initial Screen

          See Figure 1. After a few seconds the display will show a
          Gantt/Pert chart for a minimal project. It will have only a
          start milestone, a single task, and an end milestone. Here
          are some important things to note about the way a schedule
          is displayed.

          o  The Calendar - Dates run left to right across the top of
             the display. Month, date, and day-of-week (MTWTF) are
             shown. Only week-workdays are used, and there are no
             provisions for holidays.

          o  Milestones - Each Milestone is represented by an asterisk
            (*) and is shown as occurring on one day only.

          o  Tasks - Tasks are represented as equal signs (=) if they
             are on the critical path, or dash-lines (-) if they
             aren't.

          o  ID's - Each task or milestone must have a unique
             identifying number which is displayed below it ("10" for
             the "Start" Milestone).

          o  Line Numbers - Each task or milestone is represented on a
             3-row "Line". ("1" for the Start milestone, "2" for
             "Task".) You can assign the Line Number for any Task or
             Milestone, to format the Schedule the way you want.

          o The name of the Current Project is displayed in the upper
            left hand corner.

          o The amount of used capacity is displayed. Since only 3 of
            MainLine's 150 tasks are in use, the usage is quite small
            (2%)


                                                           5

 
Figure 1: Blank Project
Project: MLWORK   Edit Task  :_             Usage 2%  INS    MainLine Rev 2.0
               .----------------------+---------------------+------------------.
Press /,\,or   |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
 ESC for       |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
 Command Menu  |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|            2 | Task    .    .    .    .    .    .    .    .    .    .    .   |
|              | ===================^   .    .    .    .    .    .    .    .   |
|              |  20.    .    .    .    .    .    .    .    .    .    .    .   |
|            3 |    .    .    .    .End .    .    .    .    .    .    .    .   |
|              |    .    .    .    .*   .    .    .    .    .    .    .    .   |
|              |    .    .    .    . 30 .    .    .    .    .    .    .    .   |
|            4 |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|            5 |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|            6 |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'




                                                          6


           3.2  Moving Around - Key Commands

          You can use keyboard keys to move around and look at other
          parts of the schedule.

          You can use the UP(^) and DOWN(v) arrows to scan through the
          schedule one line at a time.

          The "PAGE UP" and "PAGE DOWN" keys will move the display one
          screen at a time.

          Pressing the RIGHT and LEFT Arrow keys moves the display
          horizontally.

          Note - If multiple Arrow or PAGE UP/DOWN keys are entered
          quickly, after a brief pause the screen will be updated only
          once. This is a great timesaver. It reduces the time spent
          waiting for the screen to be redrawn. To demonstrate this
          feature, press RightArrow three times quickly. This only
          works with multiple entries of the same key type.

          These and other key selections are listed below;

          Key                Function
          Down Arrow         Advance Screen One Line
          Up Arrow           Back Screen One Line
          Right Arrow        Move Forwards in time.
          Left Arrow         Move Backwards in Time
          PAGE DOWN          Advance to Next Screen
          PAGE UP            Go Back 1 Screen
          HOME               Move to Top-most Screen and Start of
                             Calendar
          CTRL-T             Move to Top-most Screen
          CTRL-B             Move To Bottom-most Screen
          CTRL-L             Move Horizontally Left To Start of Calendar
          CTRL-R             Move Horizontally Right to Latest Used Date
          CTRL-F             Find Task/Milestone
          +                  Follow the critical path forwards in time
          -                  Follow the critical path backwards in time
          "|"                Go To A Specific Line Number
          "\",/", or ESC     Activate Command Menu


                                                          7


          3.3  The Command Menu

          There are many commands for editing, filing, generating
          outputs, etc. The majority are activated by use of a pull-
          down menu. The menu is called up by pressing the "\", "/",
          or ESC key. (Press "/" Now)

          Note that the commands "File, Edit, Search ,Display,Print"
          are displayed at the top of the screen, and that "Filing" is
          highlighted.

          The Highlight may be moved around by pressing the right- or
          left- arrows. Try it, but then return to "Filing".

          Pressing down-arrow cause a menu to appear below the
          highlighted entry.

          With "Filing" still highlighted, hit down-arrow now and note
          that the menu choices New, Open, Save, Import, and Exit
          appear. The first entry (New) is highlighted.

          Pressing the Up- or Down Arrow key moves the highlight up
          and down. Pressing the Right- and Left- Arrow keys moves to
          adjacent menus.

          Pressing the ENTER or RETURN key cause the highlighted
          command to be executed.

          While viewing the pull-down-menu, screen movement keys no
          longer operate. Pressing ESCAPE at any time backs up one
          level in the Menu-Command line. Pressing ESCAPE when at the
          top level exits the Menu and normal screen viewing ability
          returns. (Press ESCAPE twice now.)

          From here on, sequences of using the pull-down-menu will be
          described as follows;

          "\+File+Save" means execute the series of menu choices
          starting with "\" or "/", then "Filing",  and "Store".


                                                          8

          3.4  Quick Entry - Adding a Task

          The more frequently used functions of Edit, Add, and Delete
          task may be activated directly without going through the
          pull-down menu.

          Note that the top-line of the screen  contains the phrase
          "Edit Task:" followed by a blinking cursor. Pressing the "a"
          key will cause the phrase "Add Task" to appear. Pressing "d"
          similarly switches to "Delete Task:", and "e" returns to
          "Edit Task:"

          Press "a" to cause "Add Task" to appear. Type in "25" and
          press ENTER. (All entries require termination by ENTER.)
          Enter "t" or ENTER when prompted to select a Task or
          Milestone.

          You will be asked to specify the ID of a Task or Milestone
          which the new task is to succeed - enter "20".

          You will be asked to specify the ID of a Task or Milestone
          which the new task is to preceed - enter "30". (You don't
          have to enter anything here, you could leave it blank -
          we'll just include it for this exercise.)

          A Task Data Sheet for task 25 will now appear at the bottom
          of the screen. You may edit any of the task's data entries
          by selecting a letter/number associated with the data,
          pressing ENTER, and then entering the data.
          Enter "c" (with ENTER) to edit the Title. Then enter "New
          Task".

          "New Task" should appear in the Title field of the Task Data
          Sheet.

          Enter "d" to edit the Duration. Then enter "20" for 20
          working days.

          To leave the editing mode, enter "x" for Exit.

          The full screen is displayed again. It should look like
          Figure 2.

          Note the following about the new task;
          o  It is chronologically between the "Task" and the "End".
          o  It is on line 2.
          o  It is on the critical path.

          Note 1 - Note that the screen-movement keys (Arrows, PG
          UP/DN, etc, all function while the task editor is working.)

          Note 2 - A default line number is always supplied, typically
          the same line number as that of the "After Task?" entry.
          When the Task Editor is active, you may change the line
          number as follows;
          Enter "l" to select which line the task should appear on.
          Use BACKSPACE to erase the present line number, then enter
          the new line number.

                                                          9


Figure 2: 1 Task Added
                  Project=<DEMO>      Usage = 2%             MainLine Rev 2.0
               .----------------------+---------------------+------------------.
               |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|            2 | Task    .    .    . New Task.    .    .    .    .    .    .   |
|              | ===================^===================^   .    .    .    .   |
|              |  20.    .    .    .  25.    .    .    .    .    .    .    .   |
|            3 |    .    .    .    .    .    .    .    .End .    .    .    .   |
|              |    .    .    .    .    .    .    .    .*   .    .    .    .   |
|              |    .    .    .    .    .    .    .    . 30 .    .    .    .   |
|            4 |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|            5 |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|            6 |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
|              |    .    .    .    .    .    .    .    .    .    .    .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'



                                                          10


          3.5  Storing a Project

          In order to store the edited project under a new name, do
          the following;

          Execute /+File+Save

          You will be prompted for the name to store it under - a
          default of "mlwork" is shown in brackets.

          Type "demo" for the name and press ENTER.

          The data base for this project has now been saved. The
          project could be edited further (remember to store again
          after additional changes), or you could exit, restart the
          program, and load the stored project.

          3.6  Printing Reports

          Before exiting let's generate some output reports. We'll
          just create the reports now, and examine them after exiting.

          Create a schedule report by executing

          \+Print+Partial_Schedule. Create a date report by executing
          \+Print+Date_Report

          Create a task-milestone report by executing

          \+Print+Task_Detail


          3.7  Exiting

          Let's temporarily exit.

          Enter the commands \+File+Exit



                                                        11


          3.8  Examining The Reports

          You should be back to the DOS prompt.

          Enter the command

          C:\MAINLINE>DIR

          You will get a directory listing which should include the
          following files

          1. ML.EXE - The executable MainLine file
          2. DEMO.PRJ - The data file for the demo project you have
             created.
          3. DEMO.PR1 - An auxillary data file storing text
             information.
          4. DEMO.TXT - The Schedule for DEMO
          5. DEMO.DAT - A Date Report for DEMO
          6. DEMO.RPT - A complete report with all the data of all the
             tasks and milestones in DEMO.
          7. MLJRNL.PRJ - A backup file to protect project data. (See
             Section 5.3.)
          8. MAINLINE.CFG - A configuration file storing options about
             screen appearance.

          DEMO.TXT is a text file containing the schedule. It will be
          132 columns wide. It should look like Figure 2. (Figure 2
          has been modified here to be 80 columns wide to fit better
          in this manual.)

          You can examine DEMO.TXT with the TYPE command or with a
          text editor. You can mail it to anyone on your network. You
          can send it to any ASCII printer. If you print it out in
          LANDSCAPE on a laser printer, a viewgraph/transparency can
          be made which is suitable for use in presentations.

          DEMO.DAT lists the start- and end- dates for all the tasks
          and milestones in DEMO. It is reproduced in Figure 3

          DEMO.RPT lists all tasks and milestones in DEMO, with their
          complete data - predecessors, titles, start and end dates,
          etc. It is listed in Figure 4

          Note - Any change to a .PRJ or .PR1 file could make the file
          unusable. Never try to directly edit or otherwise change a
          .PRJ or .PR1 file. Don't even try to view it with a word
          processor or text editor.


                                                          12



Figure 3: DEMO.DAT

                                       Report Date: 16-Mar-92
Task and Milestone Date Report        Project Name: demo
                                                   --------------------
Task# Typ Description                               Start      End
----- --- ----------------------------------------  ---------  ---------
 10   S   Blank               Start                 02-Mar-92  02-Mar-92
 20   T                       Task                  03-Mar-92  30-Mar-92
 25   t                       New Task              31-Mar-92  27-Apr-92
 30   F                       End                   27-Apr-92  27-Apr-92



                                                          13


Figure 4: DEMO.RPT
                                       Report Date: 16-Mar-92
Task and Milestone Detail Report      Project Name: demo
                                                   --------------------

*******************************************************************************
Task #  10     Type S    Description; Blank                 Start

Start:02-Mar-92  
End:02-Mar-92  
Duration:  0      
Wait :  0
                                                  Display Line:  1
Predecessors ;
-------------------------------------------------------------------------------

Task #  20     Type T    Description;                       Task
Start:03-Mar-92  
End:30-Mar-92  
Duration:  20     
Wait :  0
                                                  Display Line:  2
Predecessors ;  10,

-------------------------------------------------------------------------------
Task #  30     Type F    Description;                       End

Start:27-Apr-92  
End:27-Apr-92  
Duration:  0      
Wait :  0
                                                  Display Line:  3
Predecessors ;  25,
-------------------------------------------------------------------------------

Task #  25     Type t    Description;                       New Task
Start:31-Mar-92  
End:27-Apr-92  
Duration:  20     
Wait :  0
                                                  Display Line:  2
Predecessors ;  20,

-------------------------------------------------------------------------------



                                                          14

          4  Trial Run - 2nd Pass

          In the previous chapter we demonstrated the very basics;
          turning the program on, creating and storing a simple
          project, generating some reports, and exiting.

          This chapter will demonstrate in more detail the functions
          of MainLine.

          We'll start by reading back in the project that was
          previously created.


          4.1  Reading In A Project

          Enter ML to start the program. Execute the command sequence
          \+File+Open.

          Select the project "demo". You may do this either of two
          ways. Pressing ENTER will load the highlighted project.
          (Arrow keys and PAGE UP/DOWN keys move the highlight around
          the displayed list of existing project files.) Or, just type
          in the project name DEMO followed by ENTER.

          Note - Another way to load a project is to include the name
          of the project when starting Mainline. I.E. entering ML DEMO
          at the DOS prompt would have automatically loaded the DEMO
          project.


          4.2  Editing an Existing Task

          Before demonstrating more functions, lets first update the
          project to represent something a little more specific.

          Call up the Task Editor for Task 20.

          Select the Title by entering "c". Erase the present title
          using the BACKSPACE key, and enter the new title "Define".
          In a similar manner, edit the task duration (field "d") to
          be 10 days.

          Select task 25 for editing by entering "n" (for New task)
          and the Task Data Sheet for Task 25 will appear. Using the
          procedure above, change its title to "Develop".

          Select "x" to end the editing session.

          This has demonstrated how to make changes to an existing set
          of tasks or milestones.

          Note that in editing entries the cursor may be positioned
          using the right- and left-arrows, and new characters may be
          inserted by typing.


                                                          15


           4.3  Inserting, Deleting, Moving Lines

          The lines on the screen may be changed much like those in a
          spreadsheet. Blank lines may be added or deleted, or blocks
          of lines may be moved around.

          To insert some blank lines execute \+Display+Add_lines.
          When prompted, enter that you want to add lines before line
          3, and that you want to add 3 lines. Note on the screen that
          the END task has been "pushed down" 3 lines. (Remember - one
          "line" means 3 rows on the screen.)

          We don't need to demonstrate it here, but by using
          \+Display+Delete_lines you can delete a group of consecutive
          lines.

          It is not possible to delete a line that has tasks or
          milestones on it.

          You are now somewhat proficient at adding and editing tasks.

          Now proceed to add the following tasks to the project.
          o  Task 40, line 2, duration 15, title "Manufacturing" - add
             this task after task 25, and before milestone 30.
          o  Task 50, line 3, duration 30, title "Programming" - add
             this task after task 20, and before milestone 30.
          o  Task 60, line 4, duration 33, title "Marketing" - add
             this task after task 20, and before milestone 30.
          o  Task 70, line 5, duration 20, title "Testing" - add this
             task after task 25, and before milestone 30.
          The project should appear as in Figure 5. At this point, save
          the project so the work doesn't get lost.

          To move lines 5 and 6 so that they are after line 2, and
          ahead of the present line 3, execute \+Display+Move_lines.

          When prompted respond as follows;
             Move From Line = "5"
             Thru Line = "6"
             To Line = "3"

          The whole command sequence will be repeated for
          verification. Type ENTER to proceed, or "n" to abort. The
          lines should now be re-ordered as in Figure 6.

                                                          16


Figure 5: Tasks Added
                                                             MainLine Rev 2.0
               .----------------------+---------------------+------------------.
               |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|            2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |
|              | =========^===================^--------------^   .    .    .   |
|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |
|            3 |    .    . Programming  .    .    .    .    .    .    .    .   |
|              |    .    . -----------------------------^   .    .    .    .   |
|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |
|            4 |    .    . Marketing    .    .    .    .    .    .    .    .   |
|              |    .    . --------------------------------^.    .    .    .   |
|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |
|            5 |    .    .    .    .    .    . Testing .    .    .    .    .   |
|              |    .    .    .    .    .    . ===================^   .    .   |
|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |
|            6 |    .    .    .    .    .    .    .    .    .    .End .    .   |
|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |
|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'










                                                          17


Figure 6: Moved Lines
                                                             MainLine Rev 2.0
               .----------------------+---------------------+------------------.
               |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|            2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |
|              | =========^===================^--------------^   .    .    .   |
|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |
|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |
|              |    .    .    .    .    .    . ===================^   .    .   |
|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |
|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |
|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |
|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |
|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |
|              |    .    . -----------------------------^   .    .    .    .   |
|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |
|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |
|              |    .    . --------------------------------^.    .    .    .   |
|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'







                                                          18

          4.4  Deleting A Task

          Deleting a task is very straightforward.

          Press "d" to change the quick entry mode to "Delete Task"
          and enter the ID of the task or milestone to be deleted.

          (Alternatively, use the pull-down-menu to execute
          \+Edit+Delete)

          In some instances it may not be appropriate to delete a
          task, and the DELETE will be automatically aborted. This can
          occur if deleting the Task would make it impossible to
          calculate the Critical Path.

          How It Works

          The critical path is automatically calculated between a
          specified "Start" milestone and a specified "Finish"
          milestone.

          These two milestones are selected by the user. Call up the
          task data sheet and you will notice that there is a field
          called "Type". Tasks and Milestones are identified here by
          "t" and "m" respectively.

          The "S" (Start) milestone is fixed for any one project. Any
          one milestone may be assigned as the "F" (Finish) Milestone.

          The Critical path is calculated between the Start and Finish
          milestones.

          Requirements

          The only requirement is that there be a logical "path"
          between the Start and Finish milestones. An interesting
          result of this is that you may have other tasks/milestones
          which originate or terminate "in space" - no path leading
          directly from or to the Start and Finish dates. This is
          acceptable, and in many cases reflects real life. (Many
          other Project Management tools require that all tasks are
          connected together and that there are no "loose ends".)

          Moving the End Points Around

          The "Blank" project starts with exactly one Start and one
          Finish Task assigned.

          To "move" the Finish designation around, for What-If
          purposes, you may temporarily append the Finish
          characteristic to more than one milestone, then remove the
          superfluous one. Any edits which even temporarily result in
          having no Finish milestone will be rejected.

          If at any point there is more than one Start or Finish
          milestone, the critical path calculations may be wrong. This
          will be corrected once there are no superfluous Starts and
          Finishes.

                                                          19


          4.5  Adding Descriptions to Groups of Tasks

          It is helpful to add comments to groups of tasks or
          milestones.

          Comment fields may be added in the left hand field of the
          display. There are two comment fields, called Head1 and
          Head2.

          Call up the DEMO project. Edit task #20 ("Define") so that
          the Head1 field contains "Project 1" and the Head2 Field
          contains "- Hardware". Edit Task 50 ("Programming") so that
          the Head2 Field contains "- Software". Finally, edit Task 60
          ("Marketing") so that the Head2 field contains "- Other"

          The schedule should now look like Figure 7.

          When 2 or more Tasks or milestones on the same line both
          have entries in their Head1 or Head2 fields, the Heads from
          one task/milestone are arbitrarily selected for display.


          4.6  Adding A Date and Labels to The Display

          A Date field, and user-defined Labels, are displayed in the
          upper left-hand corner of the display. There are 4 Labels,
          each 15 characters long.

          The Date field is assigned or updated whenever the project
          is Stored.

          The Label fields are set by the user using the commands
          \+Display+Labels

          A menu will be presented to enter new Labels or to change
          the existing ones.

                                                          20


Figure 7: Adding Comments
                                                             MainLine Rev 2.0
               .----------------------+---------------------+------------------.
               |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|Project 1   2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |
| - Hardware   | =========^===================^--------------^   .    .    .   |
|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |
|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |
|              |    .    .    .    .    .    . ===================^   .    .   |
|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |
|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |
|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |
|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |
|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |
| - Software   |    .    . -----------------------------^   .    .    .    .   |
|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |
|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |
| - Other      |    .    . --------------------------------^.    .    .    .   |
|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'








                                                          21


Figure 8: Date and Label Fields
                                                             MainLine Rev 2.0
Label 1        .----------------------+---------------------+------------------.
Label 2        |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
Label 3        |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
Label 4        |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|Project 1   2 | Define  . Develop .    .    . Manufacturing.    .    .    .   |
| - Hardware   | =========^===================^--------------^   .    .    .   |
|              |  20.    .  25.    .    .    .  40.    .    .    .    .    .   |
|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |
|              |    .    .    .    .    .    . ===================^   .    .   |
|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |
|            4 |    .    .    .    .    .    .    .    .    .    .End .    .   |
|              |    .    .    .    .    .    .    .    .    .    .*   .    .   |
|              |    .    .    .    .    .    .    .    .    .    . 30 .    .   |
|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |
| - Software   |    .    . -----------------------------^   .    .    .    .   |
|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |
|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |
| - Other      |    .    . --------------------------------^.    .    .    .   |
|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'









                                                          22

          4.7 Multiple Editing Views

          Call up the task editor for any task. Note that, adjacent
          to the 4 date fields (Begin, Finish, Duration, Wait) there
          are 4 text fields labeled G, H, I, and J respectively. These
          4 fields may be used for any purpose, although they would
          be most convenient for providing brief notes about the 4
          adjacent date fields. Example;

          [B] Begin   : 22-Mar-94        [G] Started On Schedule
          [F] Finish  : 29-Mar-94        [H] Projected End
          [D] Duration:  5               [I] Best Estimate
          [W] Wait    :  0               [J]

          Note that by pressing the "v" key and ENTER/RETURN, the view
          of the task editor changes. Predecessor and date information
          are replaced by 4 lines of text labeled 1,2,3, and 4
          respectively. Pressing the numeric key and ENTER/RETURN
          allows each line to be edited.

          This allows a short amount of description to be appended to
          every task or milestone. The information is printed out as
          part of the normal TASK DETAIL REPORT.

          Selecting "v" again  changes the view one more time. The 10
          predecessor are displayed. The Description field of each
          predecessor is listed, as well as the predecessor's
          identifying task number. This makes it somewhat easier to
          edit predecessors.

          Selecting "v" one more time returns the Task Editor to its
          original view.

          4.8  Locating Tasks - The "Search" Function

          Features are included to make it easy to locate a particular
          task. This becomes necessary as a project grows.

          You can search through the entire project for one or more
          tasks having a particular Title or Descriptive field. Enter
          \+Search and menu entries  will be presented to search by
          Description, Head1, or Head2. Enter a word or phrase, and
          all tasks will be sequentially displayed that match the
          entry. "Near misses" will be accepted - i.e. if "Des" is
          entered, tasks or milestones having Titles of "Design",
          "Destination",and "Oldest" would all be located. (The search
          ignores the case of characters). This can be very helpful
          when the exact title is not remembered. As each found task
          is displayed, the option is presented of stopping and
          displaying the screen holding that task, of continuing the
          search, or of quitting. If you continue to search and no
          further matching tasks are found, you have the option of
          displaying the last found match, or of quitting.

          It is also possible to locate tasks directly by ID Number
          (press CTRL-F when viewing the screen) or by going to the
          tasks line if it is known ( press "|" ).

                                                          23


          4.9  The Wait Function

          It is sometimes useful to specify that a task not actually
          start  until some fixed time after its predecessors have
          completed. This could be accomplished by inserting a "wait"
          task. However, MainLine offers the simpler step of assigning
          a "wait" period for each task.

          In the Demo example, edit the [W]ait field of the task data
          sheet for task 40 to have a delay of 10 days. The results
          are shown below. The period of waiting is indicated by a
          string of "......" characters for tasks off the critical
          path, or "::::::" for tasks on the critical path.


Figure 9: Using The Task Wait Function
                                                             MainLine Rev 2.0
Label 1        .----------------------+---------------------+------------------.
Label 2        |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
Label 3        |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
Label 4        |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|Project 1   2 | Define  . Develop .    .    .    .    . Manufacturing.    .   |
| - Hardware   | =========^===================^::::::::::==============^   .   |
|              |  20.    .  25.    .    .    .    .    .  40.    .    .    .   |
|            3 |    .    .    .    .    .    . Testing .    .    .    .    .   |
|              |    .    .    .    .    .    . -------------------^   .    .   |
|              |    .    .    .    .    .    .  70.    .    .    .    .    .   |
|            4 |    .    .    .    .    .    .    .    .    .    .    .End .   |
|              |    .    .    .    .    .    .    .    .    .    .    .*   .   |
|              |    .    .    .    .    .    .    .    .    .    .    . 30 .   |
|            5 |    .    . Programming  .    .    .    .    .    .    .    .   |
| - Software   |    .    . -----------------------------^   .    .    .    .   |
|              |    .    .  50.    .    .    .    .    .    .    .    .    .   |
|            6 |    .    . Marketing    .    .    .    .    .    .    .    .   |
| - Other      |    .    . --------------------------------^.    .    .    .   |
|              |    .    .  60.    .    .    .    .    .    .    .    .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'

                                                          24


          4.10  Changing Program Configuration

          MainLine has several options for changing the appearance of
          the screen display or printed output, or for changing
          fundamental characteristics of the present project. These
          are accessed via the command \+Display+Options.

          The menu shown in Figure 10 will appear. Information about
          the current project will be displayed - the project's name,
          and its date of most recent revision. Other information
          about how MainLine is currently operating is also displayed.
          Information preceded by a letter in brackets may be changed
          using this menu.

          To change a setting, enter the bracketed letter in front of
          the setting, and then press ENTER. For some settings, a
          series of choice-prompts will follow. For others, the
          setting will automatically toggle to its only other value.

          Example - Changing The Start Date

          MainLine uses the current date as the default project start
          date. To change it, enter S followed by ENTER. When prompted
          for a new start date, enter 6-Jan-92.

          Press X followed by ENTER to leave the Options menu. The
          Calendar should be appropriately updated. When you store the
          project again, the new start date will be stored with it.

          The only restriction is that the selected date must be on a
          week-day.

          Example - Changing The Time Scale

          Projects can be displayed using either days or weeks as the
          basic unit of time. When the default, days, is used,
          approximately 4 1\2 months of activity may be displayed on
          an 80 column screen. (Wider screen styles, allowing longer
          time ranges to be displayed, are described in the following
          material.) When a scale of weeks is used, approx. 7 months
          activity can be displayed on an 80 column screen.

          On the Options menu, enter T and ENTER, and the time scale
          will automatically toggle from DAYS to WEEKS.

          When a project is stored, the time_scale in use is stored as
          part of the project. That time scale will be used when that
          project is read back in at a later time.

          Note - All Task Durations must always be entered as working-
          days, regardless of which time scale is used for displays,


                                                          25


Figure 10: Display Options Configuration Menu

.------------------------------------------------------------------------------.
!      Project                                Configuration                    !
!      ----------------------------           -----------------------          !
!            Name       : __________                Name  : __________         !
!            Rev Date   : __________            [F] File                       !
!        [S] Start Date : __________            [G] Get                        !
!                                                                              !
!      Screen                                 Printer                          !
!      ----------------------------           ---------------------            !
!        [W] Width      : ___                   [P] Print Width: ___           !
!        [C] Color/Fore : __________            [D] Display ID : ___           !
!                 /Back : __________                                           !
!        [T] Time Scale : __________                                           !
!        [I] ID Display : __________            [X] Exit                       !
!                                                                              !
!             Press Letter in [ ] To Change Function, [x] to Finish            !
!                                                                              !
!   MainLine Rev 2.0   Registered To : ____________________    Ser.No. _____   !
`------------------------------------------------------------------------------'







                                                          26


          Screen Width and Color

          Black and White display, of an 80 column-wide screen, is the
          default display mechanism. However, the use of colors and
          wider screen styles is also supported.

          Assuming your machine's graphics adapter and monitor support
          color, you may change the display colors using the Global
          Colors function [C]

          A wider time range may be displayed on the screen by
          changing the Screen Width to 105 columns using the Width
          function [W]. The 105 columns mode also provides about 50%
          more rows of displayed data. If your system supports VGA
          graphics, you will be prompted for a choice of Black/White
          display ("CGA-style" graphics) or full color. If your system
          does not support VGA graphics, only the Black/White CGA-
          style is offered.

          There are some tradeoffs to using the 105 columns-mode of
          screen display;

          o  All letters are displayed in Uppercase. (Printed outputs
          continue to use Upper and Lower case).

          o  Black/White CGA-mode runs somewhat slower than 80-columns
          mode. 105-Columns color-mode runs slower still. This is more
          noticeable on older, slower machines. On a 20 MHz 386-based
          machine, all modes run quite acceptably.


                                                          27


          Other Settings

          Here is a brief description of other settings that may be
          selected using the Options menu. See Section 6 for more
          information.

          o  [I] : Screen ID Display - Controls (yes/no) whether task
          identifying numbers are displayed below each task. This
          allows mores lines of tasks to be displayed on the screen.

          o  [P] : Printer Size - Selects "A" size 80 column output,
          or "B" size 132 column output.

          o  [D] : Printer ID Display - Similar to Screen ID Display,
          but affects printed output only.

          Configuration Files

          You can store the configuration so that it will be used
          automatically the next time MainLine is used. (This saves
          you from having to set it up every time). Pressing F and
          ENTER will file the present configuration. A default
          filename will be supplied (MainLine). Press ENTER to store
          the configuration as MainLine. You may find that there are
          different configurations you prefer to use on some
          occasions. You can set a different configuration, then store
          it under some other name. It can be recalled at a later time
          using the "Get" command (choice G in the Options Menu). The
          name of the configuration presently in use is always
          displayed in the Options menu.

          The configurations are stored in your directory with
          extension .cfg. You do not have to specify the extension
          when storing or loading a configuration file - that is done
          automatically.


                                                          28


          5  Advanced Topics

          5.1  System Capabilities

          Projects of the following sizes can be handled;

          o  Up to 150 Tasks and/or Milestones.
          o  Tasks/Milestones may be displayed on up to 1000 "Lines"
          o  Dates must fall within the range of 1-Jan-1991 to 1-Jan-
             2000.

          Attempts to exceed these values will usually not be
          accepted. It is possible that under some circumstances the
          program may accept the value and then crash.

          5.2  Following The Critical Path

          On larger projects, it may be desirable to trace the tasks
          and milestones along the critical path. Pressing the "+" and
          "-" keys moves the display forwards or backwards in time
          along the critical path.

          5.3  The Journal File - Recovering Damaged Project Files

          It is possible that at some time the operation will be
          unwillingly terminated while there are edits that have not
          been saved.

          This may occur due to a system crash (possibly due to a
          power outage), or due to some as-yet-unknown bug in the
          program. To allow recovery from this, a "backup" or
          "journal" file of editing activity is created. Every time
          you leave the text editor, the Project File of the current
          project, including edits, is copied to the file MLJRNL.PRJ.

          To recover, copy the MLJRNL.PRJ to some random project
          filename like RECOVER.PRJ. Then start MainLine again, and
          read in RECOVER as a project. If it appears to be what you
          want, exit the program and copy RECOVER.PRJ over your
          original projects' .PRJ file.



                                                          29


          5.4  Attaching Fixed Dates to Tasks or  Milestones

          A task or milestone may be entered with no predecessors,
          with its date manually entered. This is useful for
          indicating fixed or external occurrences.

          To do this, enter the task or milestone using the normal
          task addition procedure. When prompted for "After Task?"
          enter n for "none". Enter (or not) a "Before Task?". When
          the Task Editor Screen pops up, enter a [B]egin date for the
          new task or milestone.

          Thereafter, that task or milestone will appear at that date,
          regardless of other tasks or milestones in the project. (You
          can always Edit that date.)

          Note - Fixed tasks or milestones which get on the critical
          path will prevent the critical path from reaching all the
          way back to the project START milestone. There is nothing
          wrong with this, but it may at first appear to be a
          surprising result. It will be flagged as a  WARNING.

          5.5  Project Rollups

          It is often desirable to summarize a group of related tasks
          as one larger effort. The Project Rollup task provides this
          function.

          A Rollup is a special type of task whose beginning and end
          dates are linked to a collected group of tasks.

          Figure 11 demonstrates this function. Task #100 is a rollup
          task. It rolls up the results of tasks 40,70, and 90. Note
          that 100's start date equals the start date of task 40
          (earliest start of the 40,70,90). Task 100's end date equals
          the end date of task 90 (latest end date of 40,70,90) Note
          that task 70's start and end lie within the min/max ranges,
          and so task 70 does not affect task 100. (Later changes in
          start/ends of the project tasks could alter this.)

          Entering Rollup Tasks - A Rollup task is entered using the
          same process as a regular task. Enter it initially as a
          regular task. It's predecessors are the tasks it is to
          rollup. After entering the rollup task, use the TASK/EDIT
          function to change its TYPE to "R" or "r".

          Helpful Hint - On a large schedule, Rollups can be used to
          provide a concise summary of the overall project. Enter the
          whole schedule in the normal fashion. Create a page-worth of
          blank lines at the head of the schedule. Place rollups there
          which summarize the key subsections of the project.

                                                          30


Figure 11: Using Rollup Tasks
                                                             MainLine Rev 2.0
               .----------------------+---------------------+------------------.
               |_____Mar '92__________|___ Apr '92 _________|___ May '92 ______|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
Date:16-Mar-92 |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
.--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
|Blank       1 |Start    .    .    .    .    .    .    .    .    .    .    .   |
|              |*   .    .    .    .    .    .    .    .    .    .    .    .   |
|              | 10 .    .    .    .    .    .    .    .    .    .    .    .   |
|            2 |    . Rollup - 40/70/90 .    .    .    .    .    .    .    .   |
|              |    . -----------------------------^   .    .    .    .    .   |
|              |    .  100    .    .    .    .    .    .    .    .    .    .   |
|            3 | Task Task 40 . Task 50 .    .    .    .    .    .    .    .   |
|              | ====^=========^---------^   .    .    .    .    .    .    .   |
|              |  20.  40.    .  50.    .    .    .    .    .    .    .    .   |
|            4 |    .    .    . Task 90 .    .    .    .    .    .    .    .   |
|              |    .    .    . ===================^   .    .    .    .    .   |
|              |    .    .    .  90.    .    .    .    .    .    .    .    .   |
|            5 | Task 60 . Task 70 .    .    .    . Task 80 .    .    .    .   |
|              | ---------^-------------------^   . =========^   .    .    .   |
|              |  60.    .  70.    .    .    .    .  80.    .    .    .    .   |
|            6 |    .    .    .    .    .    .    .    .    .End .    .    .   |
|              |    .    .    .    .    .    .    .    .    .*   .    .    .   |
|              |    .    .    .    .    .    .    .    .    . 30 .    .    .   |
`--------------+----+----+----+----+----+----+----+----+----+----+----+----+---|
               |MTWTFMTWTFMTWTFMTWTFMT|TFMTWTFMTWTFMTWTFMTWT|MTWTFMTWTFMTWTFMTW|
               |    0    1    2    2  | 0    1    1    2    |    0    1    2   |
               |    6    3    0    7  | 3    0    7    4    |    8    5    2   |
               |     Mar '92          |    Apr '92          |    May '92       |
               `----------------------+---------------------+------------------'





                                                          31


          5.6  Renumbering Tasks and Milestones

          As a Project is used and modified over time, it may become
          desirable to renumber tasks. Work is generally easier if
          related tasks have task numbers in the same range.

          The Renumber command;

          \+Edit+Renumber

          allows this. You may renumber an individual task, a group of
          tasks, or all the tasks in the present project. You select
          the task(s) to be renumbered, and specify a point to start
          renumbering the tasks At. All tasks are renumbered from the
          starting point forwards. The tasks will have the same
          sequence as in the original range. They will be numbered in
          steps of 10. To prevent overlaps, or having multiple tasks
          with the same number, a few restrictions are imposed;

          o  The new range cannot overlap any tasks which aren't being
          renumbered.
          o  The new range cannot overlap the "old range" of tasks
          that are being renumbered.

          Any attempted renumberings which violate the rules are
          rejected.

          The rules may not seem intuitively obvious. If you
          experiment with a sample project, though, the principles
          will soon become clear.

          5.7  Copying A Group of Projects

          Very often a sequence of events (a group of tasks and
          milestones) will need to be entered multiple times in a
          project. This is simplified by using the Copy Tasks
          function. \+Tasks+Copy will lead to a menu to select a range
          of tasks for copying. Since each task must have a unique ID
          number, the menu will request a new starting point to re-
          number the copied tasks to. A sufficient block of blank
          lines is automatically inserted into the project following
          the last task to be copied. The range of tasks/milestones
          will then be copied into that area, with the same
          relationships, durations, titles and comments. It is
          advisable, but not mandatory, to modify the titles and
          comments to make it easier to distinguish the new tasks from
          the old ones.

                                                          32


           5.8  Importing Projects

          It often becomes desirable to merge together projects which
          have been developed separately. This is achieved using the
          Import command;

          \+File+Import

          Before any two projects can be merged, it is necessary to
          make sure that the two projects do not repeat any task
          numbers. This can be done easily using the Renumber function
          described above.

          It is not necessary for you to change the Line Numbers which
          are used to display the tasks. The program does this for
          you. It re-numbers the "Line Number" entry for each task so
          that the imported project starts being displayed after the
          existing project. (If you don't like this order, you can
          always change it using the Move Lines command.)

          The merged projects retain the name of the project that was
          in memory when the import started.

          If the original and imported projects have different start
          dates, the earlier date is selected as the start date for
          the merged projects.

          There are cases where projects cannot be merged. The reason
          will be displayed, along with relevant numbers. The cases
          are;

          o  The imported project cannot have tasks numbers which
             overlap the existing project.

          o  The total number of tasks in the merged project cannot
             exceed the maximum number of tasks allowed per project
             (150).

          o  The total number of lines displayed cannot exceed the
             maximum displayed for any one project (1000).

          After two projects have been merged, some additional work
          may be necessary. For example, if the two projects each have
          their own Start and End milestones, it will be necessary to
          select single Start and End milestones for the new, merged,
          project.  Also, it will probably be necessary to add links
          between various tasks in the two projects - that was
          possibly the reason for merging the projects in the first
          place.



                                                          33


          6  Command Listing

          This section describes briefly all functions that may be
          accessed by the menu-command line.

        6.1  Filing

          The following functions may be accessed by this command;

          1. New - Restarts with the "blank" project being displayed.

          2. Open - recall an existing project file. You will be
             prompted for a project name.

          3. Save - Save away the project file which is being worked
             on. A default is always given. If you're working on a file
             which was read-in, the old name is the default. You may
             store it under a new name if you wish.

          4. Import - Merge another project file with the project
             presently being worked on.

          5. Exit - Leave Program

        6.2  Edit

          This is the environment for changing tasks and milestones.

          1. Change - Select an existing Task or Milestone to change
             its data.

          2. Add Task - Add one or more new tasks.

          3. Delete - Delete an existing task or milestone.

          4. Find Task - Locate an existing task by its ID number.

          5. Renumber - Change the Task Numbers for One, Some, or All
             Tasks.

          6. Copy - Duplicate a group of tasks and milestones.

        6.3 Search

             Search for tasks by

             1. Description

             2. 1st Header

             3. Second Header

                                                          34


        6.4  Display

          1. Options - Set system options of;

             Screen Width (80 or 105 column display), Color (foreground
             and background colors),  Screen ID(Show or hide, to
             compact data on the screen), Calendar Start Date, Time
             Scale, Printer Width), Print ID (Similar to Screen ID, but
             for printed output.)

          2. Add Lines - Add Blank Lines into the display.

          3. Delete Lines - remove unused lines from the display.

          4. Move Lines - Move a block of used lines up or down.

          5. Labels - Enter or change 4 label-lines on display.

        6.5  Print

          1. Partial Schedule - Print a schedule report covering only
             the time-span presently shown on the screen. Output file =
             filename.txt

          2. All Schedule - Print a schedule report for the period
             currently shown on the display through the end of the
             project. Adjacent pages of the report will need to be
             taped together to obtain a full horizontal view. Output
             file = filename.txt

          3. Date Report - Print a report of the start and end dates
             for all tasks and milestones. Output file = filename.dat

          4. Task Detail Report - List complete information on all
             tasks and milestones in the project. Output file =
             filename.rpt.

                              

                                                          1


                      APPENDIX  A - QUICK-START INFORMATION

          A.1  Starting Up

          Decompress the program files and install in a directory such
          as C:\MAINLINE. If the progrtam was obtained as a .ZIP file
          from a BBS, it can be copied into the directory and
          decompreseed using PKUNZIP.If obtained from a Shareware
          supplier, use the supplied INSTALL.BAT file or other
          installation tool.

          The executable file is ML.EXE. To run the program, at the
          DOS prompt type ML followed by ENTER.

          A.2  Moving Around The Screen

          After a few seconds a screen will be displayed for a blank
          project.

          The calendar is displayed across the top of the screen.

          The duration of all tasks is identified with either "="'s
          (on critical path) or with "-"'s (not on critical path.) All
          milestones have a duration of 0 and are indicated with a
          "*". All tasks and milestones have unique identifying TASK
          ID numbers. These are displayed on the schedule below the
          row of symbols (-,=, or *) indicating the duration of the
          task/milestone.

          The up and down arrow keys may be used to scroll the display
          up and down one task-line at a time.

          When examining the schedule, the following other controls
          may be used;

          Key                Function
          Down Arrow         Advance Screen One Line
          Up Arrow           Back Screen One Line
          Right Arrow        Move Forwards in time.
          Left Arrow         Move Backwards in Time
          PAGE DOWN          Advance to Next Screen
          PAGE UP            Go Back 1 Screen
          HOME               Move to Top-most Screen and Start of
                             Calendar
          CTRL-T             Move to Top-most Screen
          CTRL-B             Move To Bottom-most Screen
          CTRL-L             Move Horizontally Left To Start of Calendar
          CTRL-R             Move Horizontally Right to Latest Used Date
          CTRL-F             Find Task/Milestone
          +                  Follow the critical path forwards in time
          -                  Follow the critical path backwards in time
          "|"                Go To A Specific Line Number
          "\", "/", or ESC   Activate Pull-Down Menu

                                                          2

          A.3  Calling Up Commands

          Pressing "\" , "/", or ESC calls up a pull-down menu at the top
          of the screen. The majority of commands are activated from this.

          One entry on the command line is highlighted. The highlight
          may be moved around by using the horizontal arrow keys (<-
          or ->). Pressing Down-Arrow causes a menu of choices to appear.
          One of them is highlighted. The Up- and Down-Arrows move the
          highlight. The Right- and Left-Arrows select adjacent menus.

          Pressing ENTER activates the highlighted command. Pressing
          Escape backs out of the menu system.

          The most frequently used functions of Editing, Adding, and
          Deleting tasks may also be used without going through the
          menu system. Type "e", "a", or "d" to select which function.
          Enter the task number followed by return, and the function
          will start.

          A.4  Basics of Editing and Generating Reports

          Existing Tasks and Milestones are edited by activating the
          menu  and selecting "Edit" followed by "Change". A data
          sheet will appear listing all current data on the task or
          milestone. Individual entries are selected by pressing the
          code-letter in front of the data field on the sheet - i.e.
          "d" for "duration", "c" for "description, etc. Additional
          data views may be obtained by entering "v". When done, enter
          "x" to exit the data-editor with changes, or "q" to quit
          without implementing the changes.

          New Tasks and Milestones may be added by using the menu-
          command to select "Edit" followed by "Add Task". You will be
          prompted for basic information about the task/milestone, and
          then the data sheet will appear.

          Similarly, tasks may be deleted using "Edit" followed by
          "Delete". Deletions which make it impossible to calculate
          the critical path are not accepted.

          A.5  Notes on Dates and Calculations

          o  Each project must contain one milestone designated as the
           "Start" of the Critical Path, and another designated as
           the "Finish". These selections are made with the data-
           sheet editor by entering "s" and "f" respectively in the
           "Type" field for those milestones.

          o  There must be a logical path of tasks and milestones
           between the Start and Finish milestones. There may be
           tasks and milestones which are partially or completely
           disconnected ("hanging or ending in space"), but there
           must be a set of tasks and milestones connecting the Start
           and Finish together.

          o  Only work-weekdays are used. Weekend-days, if entered,
           are rejected.

                                                          1

                              
                     APPENDIX  B - SELECTING OUTPUT FORMATS


          A principal function of MainLine is to generate compact
          schedule reports suitable for viewing on screens, mailing,
          hardcopy, or making viewgraphs for use in presentations.

          The schedule is a TEXT file which can be mailed, or printed
          in a variety of ways. A schedule printed on 8.5"x11" paper
          can be made into a viewgraph or transparency suitable for
          presentations. Use the \+Display+Options command to select
          whether the output is 80 or 132 columns wide. A schedule
          that is 132 columns wide can be printed on 11"x14.5" paper
          and reduced on a photocopier onto 8.5"x11" paper. Many
          printers provide a LANDSCAPE option which allows a schedule
          132 columns wide to be printed directly on 8.5"x11" paper.

                                                          1

                              APPENDIX  C - SERVICE


          Registered users are provided service for this program.

          Telephone service is provided at (617)489-5639

          Limited service is also provided on the INTERNET network at
          address bck@world.std.com